## PRIM-TSKG
Project | Project Code | Year | Month | Day | Carpeta Mails | Mailing code Prime | Description | TSK Response
Generales | QS00 |  |  |  | 001076-20190819-PRIM-TSKG-0001(QS00)
Generales | QS00 | 2019 | 10 | 30 | 001076-20191030-PRIM-TSKG-0002(QS00) | 001076-20191030-PRIM-TSKG - 1819 | 001076-20191030-PRIM-TSKG - 1819: Response to Notices Regarding Social Unrest and National Strike | 001076-20191108-TSKG-PRIM-1778
Generales | QS00 | 2019 | 11 | 29 | 001076-20191127-PRIM-TSKG-0003(QS00) | 001076-20191129-PRIM-TSKG - 1882 | 001076-20191129-PRIM-TSKG - 1882: Letter re Force Majeure Nov 27 (2d version) signed | 001076-20191218-TSKG-PRIM-1906/1907/1908/1909/1910
Generales | QS00 | 2020 | 01 | 02 | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1973 | Response to 001076-20191211-TSKG-PRIM-1886: Reply to:001076-20191202-PRIM-TSKG - 1887: Rejection of the Updated Schedule from October´s Monthly Report San Javier - LET-TSK-PRI-SJV-2019-003 (QS05):
Generales | QS00 | 2020 | 01 | 02 | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1974 | Rejection of the Updated Schedule from October´s Monthly Report Combarbalá - LET-TSK-PRI-COM-2019-003 (QS03):
Generales | QS00 | 2020 | 01 | 02 | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1975 | 001076-20200102-PRIM-TSKG -1975: Response to 001076-20191211-TSKG-PRIM-1885: Reply to: 001076-20191202-PRIM-TSKG - 1889: Rejection of the Updated Schedule from October´s Monthly Report Llanos Blancos - LET-TSK-PRI-LLB-2019-003 (QS02): | 001076-20200123-TSKG-PRIM-1996
Generales | QS00 | 2020 | 03 | 20 | 001076-20200319-PRIM-TSKG-0005(QS00) | 001076-20200320-PRIM-TSKG -2303 | reply to : 001076-20200316-TSKG-PRIM-2176: Updated information FM Event Covid19 Pandemic: RE: 001076-20200313-TSKG-PRIM-2174: Notification of Force Majeure due to CoVid19 Pandemic (QS00):
Generales | QS00 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0006(QS00) | 001076-20200222-PRIM-TSKG -2186 | Resppnse to TSK- actual situation of hte 5 porjects
Generales | QS00 | 2020 | 03 | 25 | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320 | RE: : 001076-20200320-TSKG-PRIM-2186: Re: 001076-20200320-PRIM-TSKG -2303: reply to : 001076-20200316-TSKG-PRIM-2176: Updated information FM Event Covid19 Pandemic: RE: 001076-20200313-TSKG-PRIM-2174::Response to Request for Guidelines and Actions on the Work due to Covid-19
Generales | QS00 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0008(QS00) | 001076-20200330-PRIM-TSKG -2332 | 001076-20200330-PRIM-TSKG -2332: 001076-20200325-TSKG-PRIM-2200: Requested Change in Work MEDIUM VOLTAGE CABLES HI-POT TEST (QS00): | 001076-20200401-TSKG-PRIM-2248
Generales | QS00 | 2020 | 04 | 22 | 001076-20200422-PRIM-TSKG-0009(QS00) | 001076-20200422-PRIM-TSKG -2440 | Requested Change in Work MEDIUM VOLTAGE CABLES HI-POT TEST (QS00)::
Generales | QS00 | 2020 | 07 | 08 | 001076-20200707-PRIM-TSKG-0010(QS00) | 001076-20200708-PRIM-TSKG -2793 | Tests after energization
Generales | QS00 | 2020 | 03 | 02 | 001076-20200302-PRIM-TSKG-0012(QS00) | 001076-20200302-PRIM-TSKG -2209 | 001076-20200302-PRIM-TSKG -2209: Letter 001076-20200302-PRIM-TSKG-0012 (QS00):- TSK ´s failure to comply with MOU | 001076-20200313-TSKG-PRIM-2173
Generales | QS00 | 2020 | 03 | 17 | 001076-20200316-PRIM-TSKG-0014(QS00) | 001076-20200317-PRIM-TSKG -2285 | 001076-20200317-PRIM-TSKG -2285: Response to the letter LET-TSK-PRI-COM-2020/001: Main utility Transformer shipment delay | 001076-20200328-TSKG-PRIM-2226
Pajonales | QS01 | 2020 | 03 | 02 | 001076-20200302-PRIM-TSKG-0002(QS01) | 001076-20200302-PRIM-TSKG -2215 | 001076-20200302-PRIM-TSKG -2215: Letter 001076-20200302-PRIM-TSKG-002 (QS01): Backfeed Delay Pajonales | 001076-20200313-TSKG-PRIM-2172
Pajonales | QS01 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0003(QS01) | 001076-20200318-PRIM-TSKG -2294 | 001076-20200318-PRIM-TSKG -2294: Response to TSK's letter LET-TSK-PRI-PAJ-2020/002 (March 13, 2020)- Force Majeure due to COVID | 001076-20200320-TSKG-PRIM-2189
Pajonales | QS01 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0004(QS01) | 001076-20200330-PRIM-TSKG -2333 | 001076-20200330-PRIM-TSKG -2333: Response to TSK´s letter LET-TSK-PRI-PAJ-2020/005 (March 27, 2020) - Suggestions to contractor for subcontrators regarding measures for COVID | 001076-20200331-TSKG-PRIM-2237
Pajonales | QS01 | 2020 | 04 | 30 | 001076-20200430-PRIM-TSKG-0005(QS01) | 001076-20200430-PRIM-TSKG -2475 | 001076-20200430-PRIM-TSKG -2475: reply to : 001076-20200427-TSKG-PRIM-2335: Quickstart Pajonales 100MW - Readiness for Signal Testing (QS01): | 001076-20200505-TSKG-PRIM-2363
Pajonales | QS01 | 2020 | 05 | 04 | 001076-20200504-PRIM-TSKG-0006(QS01) | 001076-20200504-PRIM-TSKG -2478 | 001076-20200504-PRIM-TSKG -2478: follow up 001076-20200430-PRIM-TSKG -2475: reply to : 001076-20200427-TSKG-PRIM-2335: Quickstart Pajonales 100MW - Readiness for Signal Testing (QS01):: | 001076-20200505-TSKG-PRIM-2357
Pajonales | QS01 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0007(QS01) | 001076-20200527-PRIM-TSKG -2597 | 001076-20200527-PRIM-TSKG -2597: Response to Letter LET-TSK-PRI-QS00-2020/004: MV cable test and Tan Delta | 001076-20200602-TSKG-PRIM-2480
Pajonales | QS01 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0008(QS01) | 001076-20200527-PRIM-TSKG -2598 | 001076-20200527-PRIM-TSKG -2598: Response to TSK's Letters TSK-PRI-PAJ-2020/008 and TSK-PRI-PAJ-2020/017 (April 20, 2020 and May 12,2020 respectively): Measure from Chilean Gobernment | 001076-20200609-TSKG-PRIM-2508
Pajonales | QS01 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0008(QS01) | 001076-20200222-PRIM-TSKG -2188 | 001076-20200222-PRIM-TSKG -2188: Owner´s Letter as Response to LET-TSK-PRI-PAJ-2019/002 and LET-TSK-PRI-PAJ-2019/004: Alleged force Majeure in Pajonales | 001076-20200327-TSKG-PRIM-2216
Pajonales | QS01 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0009(QS01) | 001076-20200527-PRIM-TSKG -2599 | 001076-20200527-PRIM-TSKG -2599: Response to Letter LET-TSK-PRI-PAJ-2020/014: Readiness for Signal testing | 001076-20200601-TSKG-PRIM-2476
Pajonales | QS01 | 2020 | 06 | 03 | 001076-20200602-PRIM-TSKG-0010(QS01) | 001076-20200603-PRIM-TSKG -2631 | 001076-20200603-PRIM-TSKG -2631: reply to 001076-20200522-TSKG-PRIM-2449: Pajonales 87L Test, LET-TSK-PRI-PAJ-2020/019 (QS01): | 001076-20200615-TSKG-PRIM-2522
Pajonales | QS01 | 2020 | 06 | 09 | 001076-20200605-PRIM-TSKG-0012(QS01) | 001076-20200609-PRIM-TSKG -2653 | 001076-20200609-PRIM-TSKG -2653: 001076-20200505-TSKG-PRIM-2363: Answer to: 001076-20200430-PRIM-TSKG -2475: Quickstart Pajonales 100MW - Readiness for Signal Testing, LET-TSK-PRI-PAJ-2020-013 (QS01): | 001076-20200615-TSKG-PRIM-2523
Pajonales | QS01 | 2020 | 06 | 09 | 001076-20200608-PRIM-TSKG-0013(QS01) | 001076-20200609-PRIM-TSKG -2654 | 001076-20200609-PRIM-TSKG -2654: 001076-20200504-TSKG-PRIM-2347: Answer to: 001076-20200427-PRIM-TSKG -2450: mail to TSK regarding printout, Pajonales HV main frame internonnection, LET-TSK-PRI-PAJ-2020/010 (QS01): | 001076-20200714-TSKG-PRIM-2609
Pajonales | QS01 | 2020 | 06 | 16 | 001076-20200615-PRIM-TSKG-0014(QS01) | 001076-20200616-PRIM-TSKG -2688 | 001076-20200616-PRIM-TSKG -2688: reply to : 001076-20200512-TSKG-PRIM-2407: Pajonales Permit PAS 157 Letter of Concern, LET-TSK-PRI-PAJ-2020/16 (QS01): | 001076-20200623-TSKG-PRIM-2540 / 001076-20200702-TSKG-PRIM-2570
Pajonales | QS01 | 2020 | 06 | 30 | 001076-20200630-PRIM-TSKG-0015(QS01) | 001076-20200630-PRIM-TSKG -2760 | 001076-20200630-PRIM-TSKG -2760: 001076-20200609-TSKG-PRIM-2508: 001076-20200527-PRIM-TSKG -2598: Response to TSK's Letters TSK-PRI-PAJ-2020/008 and TSK-PRI-PAJ-2020/017 (QS01): Covid 19 outbreak alleged impact on Pajonales | 001076-20200713-TSKG-PRIM-2600
Pajonales | QS01 | 2020 | 07 | 08 | 001076-20200707-PRIM-TSKG-0016(QS01) | 001076-20200708-PRIM-TSKG -2794 | 001076-20200708-PRIM-TSKG -2794: 001076-20200615-TSKG-PRIM-2522: Answer to: 001076-20200603-PRIM-TSKG-2631::HV Grantry , 87L | 001076-20200820-TSKG-PRIM-2719
Pajonales | QS01 | 2020 | 07 | 08 | 001076-20200707-PRIM-TSKG-0017(QS01) | 001076-20200708-PRIM-TSKG -2795 | 001076-20200708-PRIM-TSKG -2795: 001076-20200601-TSKG-PRIM-2476: Answer to 001076-20200527-PRIM-TSKG -2599 | 001076-20200820-TSKG-PRIM-2720
Pajonales | QS01 | 2020 | 07 | 29 | 001076-20200727-PRIM-TSKG-0018(QS01) | 001076-20200729-PRIM-TSKG -2908 | 001076-20200729-PRIM-TSKG -2908: reply to : 001076-20200713-TSKG-PRIM-2600: Answer to: Response to TSK's Letters TSK-PRI-PAJ-2020/008 and TSK-PRI-PAJ-2020/017 (QS01): covid outbreak alleged impact in Pajonales | 001076-20200821-TSKG-PRIM-2725
Llanos Blancos | QS02 | 2020 | 03 | 17 | 001076-20200316-PRIM-TSKG-0002(QS02) | 001076-20200317-PRIM-TSKG -2282 | 001076-20200317-PRIM-TSKG -2282: Response to the letter No. LET-TSK-PRI-LLB-2020/001: main utility transformer shipping | 001076-20200328-TSKG-PRIM-2224
Llanos Blancos | QS02 | 2020 | 03 | 17 | 001076-20200316-PRIM-TSKG-0003(QS02) | 001076-20200317-PRIM-TSKG -2284 | 001076-20200317-PRIM-TSKG -2284: Response to LET-TSK-PRI-LLB-2020/002 (February 14,2020) and LET-TSK-PRI-LLB-2020/003 (February 21,2020): unrestricted access to site , Llanos Blancos | 001076-20200328-TSKG-PRIM-2229
Llanos Blancos | QS02 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0004(QS02) | 001076-20200318-PRIM-TSKG -2296 | 001076-20200318-PRIM-TSKG -2296: Response to TSK's letter LET-TSK-PRI-LLB-2020/005 (March 13,2020) - Force Majeure due to covid outbreak | 001076-20200320-TSKG-PRIM-2188
Llanos Blancos | QS02 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0005(QS02) | 001076-20200330-PRIM-TSKG -2334 | 001076-20200330-PRIM-TSKG -2334: Response to TSK´s letter LET-TSK-PRI-LLB-2020/008 (March 27, 2020)- Hindreances to work due to covid | 001076-20200331-TSKG-PRIM-2238
Llanos Blancos | QS02 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0007(QS02) | 001076-20200527-PRIM-TSKG -2596 | 001076-20200527-PRIM-TSKG -2596: Response to TSK's Letters TSK-PRI-LLB-2020/014 and TSK-PRI-LLB-2020/017 (April 20,2020 and May 14,2020 respectively): alleged impact in Llanos Blancos dude to COVID | 001076-20200602-TSKG-PRIM-2478
Llanos Blancos | QS02 | 2020 | 06 | 03 | 001076-20200602-PRIM-TSKG-0008(QS02) | 001076-20200603-PRIM-TSKG -2630 | 001076-20200603-PRIM-TSKG -2630: reply to 001076-20200417-TSKG-PRIM-2306: Follow up: 001216-20200414-TSKC-PRIM-0111:MAIN ELECTRICAL EQUIPMENT - UNLOADING PLANNED DATES - KNAUF INTERNAL ACCESS BLOCKED BY LIQUID GAS TANK TRUCK, LET-TSK-PRI-LLB-2020/0013,... | 001076-20200608-TSKG-PRIM-2505
Llanos Blancos | QS02 | 2020 | 07 | 06 | 001076-20200706-PRIM-TSKG-0009(QS02) | 001076-20200706-PRIM-TSKG -2784 | 001076-20200706-PRIM-TSKG -2784: RE: 001076-20200608-TSKG-PRIM-2505: Answer to: 001076-20200603-PRIM-TSKG -2630: MAIN ELECTRICAL EQUIPMENT - UNLOADING PLANNED DATES - KNAUF INTERNAL ACCESS BLOCKED BY LIQUID GAS TANK TRUCK, LET-TSK-PRI-LLB-2020/019 (QS02) | 001076-20200821-TSKG-PRIM-2722
Llanos Blancos | QS02 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0010(QS02) | 001076-20200222-PRIM-TSKG -2190 | 001076-20200222-PRIM-TSKG -2190: Owner´s Letter as Response to LET-TSK-PRI-LLB-2019/002 and LET-TSK-PRI-LLB-2019/004: response to all 16 letters allegind force majeure in llanos Blancos | 001076-20200327-TSKG-PRIM-2219
Llanos Blancos | QS02 | 2020 | 07 | 10 | 001076-20200710-PRIM-TSKG-0011(QS02) | 001076-20200710-PRIM-TSKG -2816 | 001076-20200710-PRIM-TSKG -2816: Response to TSK´s Letter TSK-PRI-LLB-2020/018 (June 01, 2020)- alleged covid impact in llanos Blancos | 001076-20200724-TSKG-PRIM-2641
Llanos Blancos | QS02 | 2020 | 07 | 29 | 001076-20200727-PRIM-TSKG-0012(QS02) | 001076-20200729-PRIM-TSKG -2907 | Envío carta informativa Nuevo Caso de contagio COVID-19 - Producción AC Llanos Blancos (QS02):
Combarbala | QS03 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0002(QS03) | 001076-20200318-PRIM-TSKG -2292 | 001076-20200318-PRIM-TSKG -2292: Response to TSK's letter LET-TSK-PRI-COM-2020/003 (March 13,2020)- alleged impac due to covid in combarbala | 001076-20200320-TSKG-PRIM-2191
Combarbala | QS03 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0003(QS03) | 001076-20200330-PRIM-TSKG -2335 | 001076-20200330-PRIM-TSKG -2335: Response to TSK´s letter LET-TSK-PRI-COM-2020/006 (March 27, 2020)- suggestions to contractor for subcontracto regarding covid measures | 001076-20200331-TSKG-PRIM-2239
Combarbala | QS03 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0004(QS03) | 001076-20200527-PRIM-TSKG -2593 | 001076-20200527-PRIM-TSKG -2593: Response to TSK's Letters TSK-PRI-COM-2020/010 and TSK-PRI-COM-2020/013 (April 20,2020 and May 11,2020 respectively): alleged impact due to covid, combarbala | 001076-20200602-TSKG-PRIM-2479
Combarbala | QS03 | 2020 | 07 | 17 | 001076-20200713-PRIM-TSKG-0005(QS03) | 001076-20200717-PRIM-TSKG -2851 | 001076-20200717-PRIM-TSKG -2851: Response to the TSK´s Letter TSK-PRI-COM-2020/014 (June 1, 2020): alleged impact due to covind in Combarbala | 001076-20200724-TSKG-PRIM-2642
Combarbala | QS03 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0007(QS03) | 001076-20200222-PRIM-TSKG -2187 | 001076-20200222-PRIM-TSKG -2187: Owner´s Letter as Response to LET-TSK-PRI-COM-2019/002 and LET-TSK-PRI-COM-2019/004: Response to 16 letter alledging force majeure due to covind outbreak | 001076-20200327-TSKG-PRIM-2218
Los Condores | QS04 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0002(QS04) | 001076-20200318-PRIM-TSKG -2293 | 001076-20200318-PRIM-TSKG -2293: Response to TSK's letter LET-TSK-PRI-LCO-2020/001 (March 13,2020)- alleged forece majeure due to covid outbreak , Los condores | 001076-20200320-TSKG-PRIM-2190
Los Condores | QS04 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0003(QS04) | 001076-20200330-PRIM-TSKG -2336 | 001076-20200330-PRIM-TSKG -2336: Response to TSK´s letter LET-TSK-PRI-LCO-2020/004 (March 27, 2020)- Suggestions to contractor fo rSub contractor in regards to covid measures | 001076-20200331-TSKG-PRIM-2240
Los Condores | QS04 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0004(QS04) | 001076-20200527-PRIM-TSKG -2594 | 001076-20200527-PRIM-TSKG -2594: Response to TSK's Letters TSK-PRI-LCO-2020/007 and TSK-PRI-LCO-2020/010 (April 20,2020 and May 17,2020 respectively):measures taken by chilean government tha allegedly impacted on Los condores | 001076-20200608-TSKG-PRIM-2503
Los Condores | QS04 | 2020 | 06 | 30 | 001076-20200630-PRIM-TSKG-0005(QS04) | 001076-20200630-PRIM-TSKG -2758 | 001076-20200630-PRIM-TSKG -2758: 001076-20200608-TSKG-PRIM-2503: Answer to: 001076-20200527-PRIM-TSKG -2594: Response to TSK's Letters TSK-PRI-LCO-2020/007 and TSK-PRI-LCO-2020/010, LET-TSK-PRI-LCO-2020/011 (QS04): alleged impac in Los condore sdue to COVID | 001076-20200724-TSKG-PRIM-2643
Los Condores | QS04 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0009(QS04) | 001076-20200222-PRIM-TSKG -2189 | 001076-20200222-PRIM-TSKG -2189: Owner´s Letter as Response to LET-TSK-PRI-LCO-2019/002 and LET-TSK-PRI-LCO-2019/005: Resposne to 16 letters in regards to Force Majeure in los condores | 001076-20200327-TSKG-PRIM-2217
San Javier | QS05 | 2020 | 03 | 17 | 001076-20200316-PRIM-TSKG-0002(QS05) | 001076-20200317-PRIM-TSKG -2283 | 001076-20200317-PRIM-TSKG -2283: Response to the letter No. LET-TSK-PRI-SJV-2020/02: unrestricted acccess to site in San javier | 001076-20200328-TSKG-PRIM-2230
San Javier | QS05 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0003(QS05) | 001076-20200318-PRIM-TSKG -2295 | 001076-20200318-PRIM-TSKG -2295: Response to the Letter No. LET-TSK-PRI-SJV-2020/001- trnasformer shippment differ from MOU | 001076-20200328-TSKG-PRIM-2225
San Javier | QS05 | 2020 | 03 | 18 | 001076-20200318-PRIM-TSKG-0004(QS05) | 001076-20200318-PRIM-TSKG -2297 | 001076-20200318-PRIM-TSKG -2297: Response to TSK's letter LET-TSK-PRI-SJV-2020/004 (March 13,2020)- alleged Force Majeure | 001076-20200320-TSKG-PRIM-2187
San Javier | QS05 | 2020 | 03 | 30 | 001076-20200330-PRIM-TSKG-0005(QS05) | 001076-20200330-PRIM-TSKG -2337 | 001076-20200330-PRIM-TSKG -2337: Response to TSK´s letter LET-TSK-PRI-SJV-2020/007 (March 27,2020)- Suggestions to Contractor fo subcontractor in regards to COVID measures | 001076-20200331-TSKG-PRIM-2241
San Javier | QS05 | 2020 | 05 | 27 | 001076-20200526-PRIM-TSKG-0006(QS05) | 001076-20200527-PRIM-TSKG -2595 | 001076-20200527-PRIM-TSKG -2595: Response to TSK's Letters TSK-PRI-SJV-2020/012 and TSK-PRI-SJV-2020/015 (April 20,2020 and May 13, 2020, respectively): covid otbreak alleged imáct on san javier | 001076-20200608-TSKG-PRIM-2504
San Javier | QS05 | 2020 | 06 | 08 | 001076-20200608-PRIM-TSKG-0007(QS05) | 001076-20200608-PRIM-TSKG -2642 | 001076-20200608-PRIM-TSKG -2642: San Javier - Access road (QS05): | 001076-20200615-TSKG-PRIM-2524
San Javier | QS05 | 2020 | 06 | 30 | 001076-20200630-PRIM-TSKG-0008(QS05) | 001076-20200630-PRIM-TSKG -2759 | 001076-20200630-PRIM-TSKG -2759: 001076-20200608-TSKG-PRIM-2504: Answer to: 001076-20200527-PRIM-TSKG -2595: Response to TSK's Letters TSK-PRI-SJV-2020/012 and TSK-PRI-SJV-2020/015, LET-TSK-PRI-SJV-2020/016 (QS05): alleged impact due to COVID in San Javier | 001076-20200713-TSKG-PRIM-2601
San Javier | QS05 | 2020 | 07 | 26 | 001076-20200724-PRIM-TSKG-0009(QS05) | 001076-20200726-PRIM-TSKG -2877 | 001076-20200726-PRIM-TSKG -2877: RE: 001076-20200615-TSKG-PRIM-2524: Answer to: 001076-20200608-PRIM-TSKG -2642: San Javier - Access road, LET-TSK-PRI-SJV-2020/017 (QS05): Acces road Sna Javier | 001076-20200821-TSKG-PRIM-2723
San Javier | QS05 | 2020 | 02 | 22 | 001076-20200221-PRIM-TSKG-0011(QS05) | 001076-20200222-PRIM-TSKG -2191 | 001076-20200222-PRIM-TSKG -2191: Owner´s Letter as Response to LET-TSK-PRI-SJV-2019/002 and LET-TSK-PRI-SJV-2019/004: alleged force majeure - San javier | 001076-20200327-TSKG-PRIM-2220
San Javier | QS05 | 2020 | 07 | 29 | 001076-20200727-PRIM-TSKG-0010(QS05) | 001076-20200729-PRIM-TSKG -2909 | 001076-20200729-PRIM-TSKG -2909: reply to : 001076-20200713-TSKG-PRIM-2601: Answer to:001076-20200630-PRIM-TSKG -2759: Response to TSK's Letters TSK-PRI-SJV-2020/012 and TSK-PRI-SJV-2020/015, LET-TSK-PRI-SJV-2020/016 (QS05):
Combarbala | QS03 | 2020 | 08 | 11 | 001076-20200811-PRIM-TSKG-0006(QS03) | 001076-20200811-PRIM-TSKG -2932 | 001076-20200811-PRIM-TSKG -2932: Response to the TSK's Letter TSK-PRI-COM-2020/016 (July 10, 2020): covid outbreak and alleged impact in Combarbala | 001076-20200821-TSKG-PRIM-2727
Los Condores | QS04 | 2020 | 08 | 11 | 001076-20200811-PRIM-TSKG-0006(QS04) | 001076-20200811-PRIM-TSKG -2963 | 001076-20200811-PRIM-TSKG -2963: Response to the TSK's Letter TSK-PRI-LCO-2020/012 (July 10, 2020)- covid outbreak and alleged impact in Los Condores | 001076-20200821-TSKG-PRIM-2726
Llanos Blancos | QS02 | 2020 | 08 | 11 | 001076-20200811-PRIM-TSKG-0013(QS02) | 001076-20200811-PRIM-TSKG -2964 | 001076-20200811-PRIM-TSKG -2964: Response to the TSK's Letter TSK-PRI-LLB-2020/023 (July 13, 2020) :covid outbreak and alleged impact in Llanos Blancos | 001076-20200821-TSKG-PRIM-2728
Pajonales | QS01 | 2020 | 08 | 11 | 001076-20200811-PRIM-TSKG-0019(QS01) | 001076-20200811-PRIM-TSKG -2965 | 001076-20200811-PRIM-TSKG -2965: Response to the TSK's Letter TSK-PRI-PAJ-2020/027 (July 14, 2020): covid outbreak and alleged impact in Pajonales | 001076-20200821-TSKG-PRIM-2724
General | QS00 | 2020 | 08 | 20 | PEQ-2020-049 | 001076-20200820-PRIM-TSKG -3002 | 001076-20200820-PRIM-TSKG -3002: Surge in Safety Incidents: | 001076-20200923-TSKG-PRIM-2823
Pajonales | QS01 | 2020 | 08 | 20 | 001076-20200819-PRIM-TSKG-0020(QS01) | 001076-20200820-PRIM-TSKG -3004 | 001076-20200820-PRIM-TSKG -3004: Response to TSK´s Letter TSK-PRI-PAJ-2020/025 (July 10, 2020): covid outbreak and alleged impact on Pajonales | 001076-20200921-TSKG-PRIM-2813
Pajonales | QS01 | 2020 | 08 | 31 | 001076-20200831-PRIM-TSKG-0021(QS01) | 001076-20200831-PRIM-TSKG -3039 | Letter 001076-20200831-PRIM-TSKG-0021(QS01) - Commissioning Quality Failure:
General | QS00 | 2020 | 09 | 14 | 001076-20200914-PRIM-TSKG-0011(QS00) | 001076-20200914-PRIM-TSKG -3106 | Resp to LET-TSK-PRI-QS00-2020-005- Spare parts | 001076-20201026-TSKG-PRIM-2882 | LET-TSK-PRIM-QS00-2020-011
General | QS00 | 2020 | 10 | 5 | 001076-20201002-PRIM-TSKG-0013 (QS00) | 001076-20201005-PRIM-TSKG -3185 | erosion affecting several slopes in Los Condores , Combarbala and San Jaiver
General | QS00 | 2020 | 11 | 5 | 001076-20201104-PRIM-TSKG-0015 (QS00) | 001076-20201105-PRIM-TSKG -3314 | Labor lawsuits filed against Owner and its affiliates | 001076-20201204-TSKG-PRIM-2964 | LET-TSK-PRI-QS00-2020-013
Pajonales | QS01 | 2020 | 11 | 18 | 001076-20201118-PRIM-TSKG-0022 (QS01) | 001076-20201118-PRIM-TSKG -3370 | response to Notice to Owner. Pajonales Mechanical Completion
General | QS00 | 2020 | 12 | 7 | 001076-20201205-PRIM-TSKG-0016 (QS00) | 001076-20201207-PRIM-TSKG -3460 | reply to 001076-20200930-TSKG-PRIM-2840: Answer to: 001076-20200916-PRIM-TSKG -3112: FINAL APPROVAL FOR ANY HABITABLE BUILDINGS (QS00):
General | QS00 | 2020 | 12 | 14 | 001076-20201210-PRIM-TSKG-0017(QS00) | 001076-20201214-PRIM-TSKG -3488 | 001076-20201214-PRIM-TSKG -3488: Letter 001076-20201210-PRIM-TSKG-0017(QS00) - Arch Flash Studies and Labeling: arc flash study | 001076-20210112-TSKG-PRIM-3044 | LET-TSK-PRI-QS00-2021-001
General | QS00 | 2020 | 12 | 16 | 001076-20201214-PRIM-TSKG-0018(QS00) | 001076-20201216-PRIM-TSKG -3496 | reply to : 001076-20201204-TSKG-PRIM-2964: Answer to 001076-20201105-PRIM-TSKG -3314: 001076-20201104-PRIM-TSKG-0015 (QS00) - Labor lawsuits filed against Owner and its affiliates (QS00):
Pajonales | QS01 | 2020 | 12 | 30 | 001076-20201224-PRIM-TSKG-0023 (QS01) | 001076-20201230-PRIM-TSKG -3542 | High Genset Temperature Issue and CFD Analysis - Pajonales:
Pajonales | QS01 | 2021 | 01 | 5 | 001076-20210105-PRIM-TSKG-0025 (QS01) | 001076-20210105-PRIM-TSKG -3566 | 001076-20210105-PRIM-TSKG -3566: Pajonales- Owners Notice of Substantial Completion
Pajonales | QS01 | 2021 | 01 | 7 | 001076-20210105-PRIM-TSKG-0024 (QS01) | 001076-20210107-PRIM-TSKG -3570 | 001076-20210107-PRIM-TSKG -3570: Pajonales- Startup venting issue with the fuel Delivery System to Powerhouses:
Pajonales | QS01 | 2021 | 01 | 12 | 001076-20210112-PRIM-TSKG-0026 (QS01) | 001076-20210112-PRIM-TSKG -3588 | Pajonales- Standby Letter of Credit No. 09615698
Pajonales | QS01 | 2021 | 01 | 22 | 001076-20210121-PRIM-TSKG-0027(QS01) | RE_ 001076-20201231-TSKG-PRIM-3022 | RE: 001076-20201231-TSKG-PRIM-3022: Notice of Achievement. Pajonales 100MW Substantial Completion | 001076-20210201-TSKG-PRIM-3096 | LET-TSK-PRI-PAJ-2021-001
Pajonales | QS01 | 2021 | 02 | 7 | 001076-20210207-PRIM-TSKG-0028 (QS01) | 001076-20210207-PRIM-TSKG -3657 | 001076-20210207-PRIM-TSKG -3657: Owner´s Letter - Retainage of Pajonlaes Project (QS01): | 001076-20210225-TSKG-PRIM-3178 | LET-TSK-PRI-PAJ-2021-003
Pajonales | QS01 | 2021 | 02 | 22 | 001076-20210221-PRIM-TSKG-0029 (QS01) | 001076-20210222-PRIM-TSKG -3751 | 001076-20210222-PRIM-TSKG -3751: 001076-20210201-TSKG-PRIM-3096: 001076-20201231-TSKG-PRIM-3022: Notice of Achievement. Pajonales 100MW Substantial Completion (QS01): | 001076-20210501-TSKG-PRIM-3362
Los Condores | QS04 | 2021 | 02 | 24 | 001076-20210224-PRIM-TSKG-0007 (QS04) | 001076-20210224-PRIM-TSKG -3782 | 001076-20210224-PRIM-TSKG-0007 (QS04) - Substantial completion Los condores (QS04):
Los Condores | QS04 | 2021 | 02 | 26 | 001076-20210226-PRIM-TSKG-0008 (QS04) | 001076-20210226-PRIM-TSKG -3796 | 001076-20210226-PRIM-TSKG -3796: Response to 001076-20201119-TSKG-PRIM-3165: Notice to Owner. Los Condores Mechanical Completion (QS04):
San Javier | QS05 | 2021 | 03 | 15 | 001076-20210315-PRIM-TSKG-0012 (QS05) | 001076-20210315-PRIM-TSKG -3882 | 001076-20210315-PRIM-TSKG -3882: Letter 001076-20210315-PRIM-TSKG-0012 (QS05) - Change in Site Manager San Javier ( QS05): | 001076-20210322-TSKG-PRIM-3264 | LET-TSK-PRI-SJV-2021-001
Llanos Blancos | QS02 | 2021 | 03 | 15 | 001076-20210315-PRIM-TSKG-0014 (QS02) | 001076-20210315-PRIM-TSKG -3881 | 001076-20210315-PRIM-TSKG -3881: Letter 001076-20210315-PRIM-TSKG-0014(QS02) - Change in Site Manager Llanos Blancos ( QS02): | 001076-20210322-TSKG-PRIM-3263 | LET-TSK-PRI-LLB-2021-001
General | QS00 | 2021 | 03 | 18 | 001076-20210319-PRIM-TSKG-0020(QS00) | 001076-20210319-PRIM-TSKG -3894 | 001076-20210319-PRIM-TSKG -3894: 001076-20210316-TSKG-PRIM-3247: Response to Prime's suggested Change In Works Combarbalá Llanos Blancos and San Javier (QS00):
General | QS00 | 2021 | 03 | 20 | 001076-20210320-PRIM-TSKG-0021(QS00) | 001076-20210320-PRIM-TSKG -3901 | 001076-20210320-PRIM-TSKG -3901: Letter 001076-20210320-PRIM-TSKG-0021(QS00) - Subcontractor Dissemintaion of False Information:
Llanos Blancos | QS02 | 2021 | 03 | 25 | 001076-20210325-PRIM-TSKG-0015(QS02) | 001076-20210325-PRIM-TSKG -3915 | Mr. Jose Riobello incident
Combarbala | QS03 | 2021 | 03 | 28 | 001076-20210328-PRIM-TSKG-0008 (QS03) | 001076-20210329-PRIM-TSKG -3916 | 001076-20210308-TSKG-PRIM-3224: Response to 001076-20210305-PRIM-TSKG -3823: Response to 001076-20210222-TSKG-PRIM-3169: Combarbalá Sewage System (QS03)::
General | QS00 | 2021 | 04 | 21 | 001076-20210421-PRIM-TSKG-0022 (QS00) | 001076-20210421-PRIM-TSKG -3964 | 001076-20210421-PRIM-TSKG -3964: Letter 001076-20210421-PRIM-TSKG-0022 (QS00) - Notification of Board Approval of Letter Agreement Executed April 15, 2021:
General | QS00 | 2021 | 04 | 29 | 001076-20210429-PRIM-TSKG-0023(QS00) | 001076-20210429-PRIM-TSKG -3991 | 001076-20210429-PRIM-TSKG -3991: Owner´s Letter - Quality Control of Fuel Tanks ( QS00):
Los Condores | QS04 | 2021 | 05 | 21 | 001076-20210521-PRIM-TSKG-0010 (QS04) | 001076-20210521-PRIM-TSKG -4058 | 001076-20210521-PRIM-TSKG -4058: Letter 001076-20210521-PRIM-TSKG-0010 (QS04)
General | QS00 | 2021 | 05 | 28 | 001076-20210528-PRIM-TSKG-0024(QS00) | 001076-20210528-PRIM-TSKG -4069 | 001076-20210528-PRIM-TSKG -4069: Letter 001076-20210528-PRIM-TSKG-0024(QS00) - Assistance Plan Letter Agreement: | 001076-20210604-TSKG-PRIM-3432 | LET-TSK-PRI-LLB-2021-002
Pajonales | QS01 | 2021 | 05 | 28 | 001076-20210528-PRIM-TSKG-0030(QS01) | 001076-20210528-PRIM-TSKG -4070 | 001076-20210528-PRIM-TSKG -4070: Letter 001076-20210528-PRIM-TSKG-0030(QS01)- Delay Liquidated Damages: | 001076-20210614-TSKG-PRIM-3456 / 001076-20210709-TSKG-PRIM-3517 | LET-TSK-PRI-PAJ-2021-005 / LET-TSK-PRI-PAJ-2021-006
General | QS00 | 2021 | 06 | 24 | 001076-20210624-PRIM-TSKG-0026 (QS00) | 001076-20210624-PRIM-TSKG -4151 | 001076-20210624-PRIM-TSKG -4151: Quickstart - Arc Flash study- Safety issue:
Combarbala | QS03 | 2021 | 06 | 30 | 001076-20210630-PRIM-TSKG-0009 (QS03) | 001076-20210630-PRIM-TSKG -4164 | 001076-20210630-PRIM-TSKG -4164: Response to 001076-20210625-TSKG-PRIM-3491: Response to 001076-20210626-PRIM-TSKG -4154: 001076-20210625-TSKG-PRIM-3488: Response to 001076-20210624-PRIM-TSKG -4152: Response to 001076-20210624-TSKG-PRIM-3485: Combarbal... | 001076-20210707-TSKG-PRIM-3513 | LET-TSK-PRI-COM-2021-004
Combarbala | QS03 | 2021 | 07 | 1 | 001076-20210701-PRIM-TSKG-0010 (QS03) | 001076-20210701-PRIM-TSKG -4168 | 001076-20210701-PRIM-TSKG -4168: Response to 001076-20210627-TSKG-PRIM-3492: Notice to Owner. Achievement of Substantial Completion QSCOM75MW (QS03):
Pajonales | QS01 | 2021 | 07 | 27 | 001076-20210727-PRIM-TSKG-0031 (QS01) | 001076-20210727-PRIM-TSKG -4253 | 001076-20210727-PRIM-TSKG -4253: Pajonales - Status of Final Completion | 001076-20210818-TSKG-PRIM-3625 | LET-TSK-PRI-PAJ-2021-007
San Javier | QS05 | 2021 | 08 | 12 | 001076-20210812-PRIM-TSKG-0013 (QS05) | 001076-20210812-PRIM-TSKG -4317 | 001076-20210812-PRIM-TSKG -4317: San Javier- Owner´s Letter No. 001076-20210812-PRIM-TSKG-0013 (QS05): | 001076-20211001-TSKG-PRIM-3758 | LET-TSK-PRI-SJV-2021-004
Los Condores | QS04 | 2021 | 08 | 25 | 001076-20210825-PRIM-TSKG-0011 (QS04) | 001076-20210825-PRIM-TSKG -4357 | 001076-20210825-PRIM-TSKG -4357: Letter 001076-20210825-PRIM-TSKG-0011 (QS04): CCC Los Condores | 001076-20210901-TSKG-PRIM-3656 | LET-TSK-PRI-LCO-2021-006
Llanos Blancos | QS02 | 2021 | 08 | 28 | 001076-20210828-PRIM-TSKG-0016 (QS02) | 001076-20210828-PRIM-TSKG -4368 | 001076-20210828-PRIM-TSKG -4368: Letter 001076-20210828-PRIM-TSKG-0016 (QS02) - llanos Blancos Schedule | 001076-20210906-TSKG-PRIM-3681 | LET-TSK-PRI-LLB-2021-003
Los Condores | QS04 | 2021 | 09 | 10 | 001076-20210910-PRIM-TSKG-0012 (QS04) | 001076-20210910-PRIM-TSKG -4408 | 001076-20210910-PRIM-TSKG -4408: Los Condores- Owner´s Letter No. 001076-20210910-PRIM-TSKG-0012 (QS04): - CCC Los Condores | 001076-20210910-TSKG-PRIM-3696 / 001076-20211106-TSKG-PRIM-3839 | LET-TSK-PRI-COM-2021-004 / LET-TSK-PRI-LCO-2021-007
Combarbala | QS03 | 2021 | 09 | 11 | 001076-20210911-PRIM-TSKG-0012 (QS03) | 001076-20210911-PRIM-TSKG -4413 | Combarbalá - Notice to Contractor of Assuming Care, Custody and Control ( QS03)
Combarbala | QS03 | 2021 | 09 | 11 | 001076-20210910-PRIM-TSKG-0012 (QS03) | 001076-20210911-PRIM-TSKG -4413 | 001076-20210911-PRIM-TSKG -4413: Combarbalá - Notice to Contractor of Assuming Care, Custody and Control ( QS03)
Llanos Blancos | QS02 | 2021 | 10 | 13 | 001076-20211013-PRIM-TSKG-0019 (QS02) | 001076-20211013-PRIM-TSKG -4508 | Letter 001076-20211013-PRIM-TSKG-0019 (QS02)
San Javier | QS05 | 2021 | 10 | 21 | 001076-20211020-PRIM-TSKG-0014 (QS05) | 001076-20211021-PRIM-TSKG -4528 | Letter 001076-20211020-PRIM-TSKG-0014 (QS05)-Rainwater ingress into Exhaust Gas Duct
General | QS00 | 2021 | 10 | 21 | 001076-20211020-PRIM-TSKG-0028 (QS00) | 001076-20211021-PRIM-TSKG -4529 | Letter 001076-20211020-PRIM-TSKG-0028 (QS00)-Radiator Fan design temperature
General | QS00 | 2021 | 10 | 23 | 001076-20211023-PRIM-TSKG-0029 (QS00) | 001076-20211023-PRIM-TSKG -4531 | Letter 001076-20211023-PRIM-TSKG-0029 (QS00)
San Javier | QS05 | 2021 | 12 | 10 | 001076-20211210-PRIM-TSKG-0015 (QS05) | 001076-20211210-PRIM-TSKG -4678 | San Javier - Owner´s Letter No. 001076-20211210-PRIM-TSKG-0015 (QS05)
San Javier | QS05 | 2021 | 12 | 20 | 001076-20211220-PRIM-TSKG-0016 (QS05) | 001076-20211220-PRIM-TSKG -4712 | San Javier - Owner´s letter No. 001076-20211220-PRIM-TSKG-0016 (QS05)
Los Condores | QS04 | 2021 | 12 | 20 | 001076-20211220-PRIM-TSKG-0013 (QS04) | 001076-20211220-PRIM-TSKG -4713 | Los Condores - Owner´s Letter No. 001076-2021120-PRIM-TSKG-0013 (QS04)
San Javier | QS05 | 2021 | 12 | 21 | 001076-20211221-PRIM-TSKG-0017 (QS05) | 001076-20211221-PRIM-TSKG -4715 | San Javier- Owner´s letter No. 001076-20211221-PRIM-TSKG-0017 (QS05)
San Javier | QS05 | 2021 | 12 | 23 | 001076-20211222-PRIM-TSKG-0018 (QS05) | 001076-20211222-PRIM-TSKG -4720 | San Javier- Owner´s Letter No. 001076-20211222-PRIM-TSKG-0018 (QS05)
Llanos Blancos | QS02 | 2021 | 12 | 23 | 001076-20211222-PRIM-TSKG-0020 (QS02) | 001076-20211222-PRIM-TSKG -4721 | Llanos Blancos- Owner´s Letter No. 001076-20211222-PRIM-TSKG-0020 (QS02)
San Javier | QS05 | 2022 | 01 | 1 | 001076-20220101-PRIM-TSKG-0019 (QS05) | 001076-20220101-PRIM-TSKG -4761 | San Javier - Notice to Contractor of Assuming Care Custody and Control
Llanos Blancos | QS02 | 2022 | 01 | 4 | 001076-20220104-PRIM-TSKG-0021 (QS02) | 001076-20220104-PRIM-TSKG -4771 | Llanos Blancos - Notice to Contractor of Assuming Care Custody and Control
General | QS00 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0030 (QS00) | 001076-20220105-PRIM-TSKG -4777 | reply to 001076-20210921-TSKG-PRIM-3730: CiW #38 (QS02)
Combarbala | QS03 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0013 (QS03) | 001076-20220105-PRIM-TSKG -4778 | reply to 001076-20210222-TSKG-PRIM-3169: Combarbalá Sewage System (QS03)
Llanos Blancos | QS02 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0022 (QS02) | 001076-20220105-PRIM-TSKG -4779 | reply to 001076-20210504-TSKG-PRIM-3368: Answer to: 001076-20210427-PRIM-TSKG -3985:CIW SEWAGE SYSTEM FOR CONSTRUCTION . ENVIRONMENTAL RESTRAINTS & DRAWING (QS02)
Llanos Blancos | QS02 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0023 (QS02) | 001076-20220105-PRIM-TSKG -4780 | reply to 001076-20210825-TSKG-PRIM-3643: Quickstart Llanos Blancos - New ECAP approved by CEN. Change in Work due to new implementation of signals and associated tests. (QS02)
San Javier | QS05 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0020 (QS05) | 001076-20220105-PRIM-TSKG -4781 | reply to TSKG-001076-00-DPR-GP-0006, San Javier access road
General | QS00 | 2022 | 01 | 5 | 001076-20220105-PRIM-TSKG-0031 (QS00) | 001076-20220105-PRIM-TSKG -4784 | Owner´s letter No. 001076-20220105-PRIM-TSKG-0031 (QS00) | 001076-20220113-TSKG-PRIM-4029 | LET-TSK-PRI-QS00-2022-001
San Javier | QS05 | 2022 | 01 | 12 | 001076-20220112-PRIM-TSKG-0021 (QS05) | 001076-20220112-PRIM-TSKG -4801 | San Javier - Owner´s letter 001076-20220112-PRIM-TSKG-0021 (QS05)
Llanos Blancos | QS02 | 2022 | 01 | 12 | 001076-20220112-PRIM-TSKG-0024 (QS02) | 001076-20220112-PRIM-TSKG -4800 | Llanos Blancos- Owner´s comments to Blackstart test
General | QS00 | 2022 | 01 | 14 | 001076-20220114-PRIM-TSKG-0032 (QS00) | 001076-20220114-PRIM-TSKG -4805 | Quickstart Projects -Owner´s letter No. 001076-20220114-PRIM-TSKG-0032 (QS00) - Subcontractor liabilities | 001076-20220117-TSKG-PRIM-4034 | LET-TSK-PRI-QS00-2022-002
General | QS00 | 2022 | 01 | 17 | 001076-20220117-PRIM-TSKG-0033 (QS00) | 001076-20220117-PRIM-TSKG -4806 | All Sites - Owner´s letter No. 001076-20220117-PRIM-TSKG-0033 (QS00)
General | QS00 | 2022 | 01 | 19 | 001076-20220119-PRIM-TSKG-0034 (QS00) | 001076-20220119-PRIM-TSKG -4817 | Subcontractor liabilities Owners response | 001076-20220127-TSKG-PRIM-4052 | LET-TSK-PRI-QS00-2022-003
General | QS00 | 2022 | 02 | 9 | 001076-20220209-PRIM-TSKG-0035 (QS00) | 001076-20220209-PRIM-TSKG -4886 | Subcontractor Payments | 001076-20220210-TSKG-PRIM-4081 | LET-TSK-PRI-QS00-2022-004
General | QS00 | 2022 | 02 | 15 | 001076-20220215-PRIM-TSKG-0036 (QS00) | 001076-20220215-PRIM-TSKG -4908 | Draft and Final invoices January 2022
Los Condores | QS04 | 2022 | 02 | 21 | 001076-20220221-PRIM-TSKG-0015 (QS04) | 001076-20220221-PRIM-TSKG -4927 | Damaged Equipment due to Prime's wrongful operation
Llanos Blancos | QS02 | 2022 | 02 | 21 | 001076-20220221-PRIM-TSKG-0025 (QS02) | 001076-20220221-PRIM-TSKG -4928 | To complement 001076-20220112-PRIM-TSKG -4800 Llanos Blancos- Owner´s comments to Blackstart test
General | QS00 | 2022 | 03 | 1 | 001076-20220301-PRIM-TSKG-0037 (QS00) | 001076-20220301-PRIM-TSKG -4935 | Invoices Requirements
Llanos Blancos | QS02 | 2022 | 03 | 8 | 001076-20220308-PRIM-TSKG-0026 (QS02) | 001076-20220308-PRIM-TSKG -4950 | BlackStart capabilities
General | QS00 | 2022 | 03 | 11 | 001076-20220311-PRIM-TSKG-0038 (QS00) | 001076-20220311-PRIM-TSKG -4972 | Follow Up - 001076-20220301-PRIM-TSKG -4935: Owner´s letter No. 001076-20220301-PRIM-TSKG-0037 (QS00) - Invoices Requirements
General | QS00 | 2022 | 03 | 17 | 001076-20220317-PRIM-TSKG-0039 (QS00) | 001076-20220317-PRIM-TSKG -4990 | Follow up 001076-20220311-PRIM-TSKG -4972: Follow Up - 001076-20220301-PRIM-TSKG -4935: Owner´s letter No. 001076-20220301-PRIM-TSKG-0037 (QS00) - Invoices Requirements::: | 001076-20220318-TSKG-PRIM-4131 | LET-TSK-PRI-QS00-2022-006
Combarbalá | QS03 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0014 (QS03) | 001076-20220323-PRIM-TSKG -5012 | Status of Final Completion Requirements - Combarbala
Los Condores | QS04 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0016 (QS04) | 001076-20220323-PRIM-TSKG -5015 | Status of Final Completion Requirements - Los Condores
San Javier | QS05 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0022 (QS05) | 001076-20220323-PRIM-TSKG -5014 | Status of Final Completion Requirements - San Javier
Llanos Blancos | QS02 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0027 (QS02) | 001076-20220323-PRIM-TSKG -5013 | Status of Final Completion Requirements - Llanos Blancos
Pajonales | QS01 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0032 (QS01) | 001076-20220323-PRIM-TSKG -5016 | Status of Final Completion Requirements - Pajonales
General | QS00 | 2022 | 03 | 23 | 001076-20220323-PRIM-TSKG-0040 (QS00) | 001076-20220323-PRIM-TSKG -5011 | Requirements and payment of Contractor´s invoice | 001076-20220328-TSKG-PRIM-4145 | LET-TSK-PRI-QS00-2022-007
San Javier | QS05 | 2022 | 03 | 29 | 001076-20220329-PRIM-TSKG-0023 (QS05) | 001076-20220329-PRIM-TSKG -5018 | Genst step-Up transformers - Alarm and Trip limits | 001076-20220411-TSKG-PRIM-4169 | LET-TSK-PRI-SJV-2022-001
Llanos Blancos | QS02 | 2022 | 03 | 29 | 001076-20220329-PRIM-TSKG-0028 (QS02) | 001076-20220329-PRIM-TSKG -5019 | SCADA SAT test | 001076-20220418-TSKG-PRIM-4178 | LET-TSK-PRI-QS00-2022-008
General | QS00 | 2022 | 03 | 31 | 001076-20220331-PRIM-TSKG -0040 (QS00) | 001076-20220331-PRIM-TSKG -5028 | Requirements and payment of Contractor´s invoice
General | QS00 | 2022 | 04 | 5 | 001076-20220405-PRIM-TSKG-0042 (QS00) | 001076-20220405-PRIM-TSKG -5033 |  | 001076-20220411-TSKG-PRIM-4168 | LET-TSK-PRI-QS00-2022-009
General | QS00 | 2022 | 04 | 11 | 001076-20220411-PRIM-TSKG-0043 (QS00) | 001076-20220411-PRIM-TSKG -5050 | Repayment of $8M Advance Payment | 001076-20220413-TSKG-PRIM-4174 | LET-TSK-PRI-QS00-2022-010
General | QS00 | 2022 | 04 | 11 | 001076-20220411-PRIM-TSKG-0044 (QS00) | 001076-20220411-PRIM-TSKG -5051 | Delay Liquidated Damages | 001076-20220413-TSKG-PRIM-4175 | LET-TSK-PRI-QS00-2022-011
General | QS00 | 2022 | 04 | 13 | 001076-20220413-PRIM-TSKG-0045 (QS00) | 001076-20220413-PRIM-TSKG -5056 |  | 001076-20220427-TSKG-PRIM-4190 | LET-TSK-PRI-QS00-2022-012
General | QS00 | 2022 | 04 | 18 | 001076-20220418-PRIM-TSKG-0046 (QS00) | 001076-20220418-PRIM-TSKG -5060
General | QS00 | 2022 | 04 | 21 | 001076-20220421-PRIM-TSKG-0047 (QS00) | 001076-20220421-PRIM-TSKG -5071 | as Built drawings
San Javier | QS05 | 2022 | 04 | 26 | 001076-20220426-PRIM-TSKG-0024 (QS05) | 001076-20220426-PRIM-TSKG -5087 | Letter SJV Water issues | 001076-20220429-TSKG-PRIM-4197 | LET-TSK-PRI-SJV-2022-002
General | QS00 | 2022 | 04 | 27 | 001076-20220427-PRIM-TSKG-0048 (QS00) | 001076-20220427-PRIM-TSKG -5093
General | QS00 | 2022 | 05 | 5 | 001076-20220505-PRIM-TSKG-0049 (QS00) | 001076-20220505-PRIM-TSKG -5104
General | QS00 | 2022 | 05 | 5 | 001076-20220505-PRIM-TSKG-0050 (QS00) | 001076-20220505-PRIM-TSKG -5105
General | QS00 | 2022 | 05 | 12 | 001076-20220512-PRIM-TSKG-0051 (QS00) | 001076-20220512-PRIM-TSKG -5132
General | QS00 | 2022 | 05 | 28 | 001076-20220528-PRIM-TSKG-0052 (QS00) | 001076-20220528-PRIM-TSKG -5187 |  | 001076-20220531-TSKG-PRIM-4256 | LET-TSK-PRI-QS00-2022-014
General | QS00 | 2022 | 06 | 1 | 001076-20220601-PRIM-TSKG-0053 (QS00) | 001076-20220601-PRIM-TSKG -5195 | Response to 001076-20220517-TSKG-PRIM-4233 Response to Invoice for Arbitration Award (QS00) | 001076-20220624-TSKG-PRIM-4298 | LET-TSK-PRI-QS00-2022-016
Llanos Blancos | QS02 | 2022 | 06 | 10 | 001076-20220610-PRIM-TSKG-0029 (QS02) | 001076-20220610-PRIM-TSKG -5210
General | QS00 | 2022 | 06 | 10 | 001076-20220610-PRIM-TSKG-0054 (QS00) | 001076-20220610-PRIM-TSKG -5211
General | QS00 | 2022 | 06 | 15 | 001076-20220610-PRIM-TSKG-0055 (QS00) | 001076-20220615-PRIM-TSKG -5223 | Contractor´s invoices related April 2022
General | QS00 | 2022 | 06 | 20 | 001076-20220620-PRIM-TSKG-0056 (QS00) | 001076-20220620-PRIM-TSKG -5235
General | QS00 | 2022 | 07 | 15 | 001076-20220715-PRIM-TSKG-0057 (QS00) | 001076-20220715-PRIM-TSKG -5278
General | QS00 | 2022 | 07 | 27 | 001076-20220727-PRIM-TSKG-0058 (QS00) | 001076-20220727-PRIM-TSKG -5312 | Pending Critical Contractor Permits | 001076-20220808-TSKG-PRIM-4344 | LET-TSK-PRI-QS00-2022-017
General | QS00 | 2022 | 07 | 27 | 001076-20220727-PRIM-TSKG-0059 (QS00) | 001076-20220727-PRIM-TSKG -5313 | Slopes integrity failures, flooding of powerhouses and drainage of electical trenches
General | QS00 | 2022 | 08 | 15 | 001076-20220815-PRIM-TSKG-0060 (QS00) | 001076-20220815-PRIM-TSKG -5323
General | QS00 | 2022 | 08 | 17 | 001076-20220817-PRIM-TSKG-0061 (QS00) | 001076-20220817-PRIM-TSKG -5346
Combarbalá | QS03 | 2022 | 08 | 31 | 001076-20220831-PRIM-TSKG-0016 (QS03) | 001076-20220831-PRIM-TSKG -5365
General | QS00 | 2022 | 09 | 6 | 001076-20220906-PRIM-TSKG-0015 (QS03) | 001076-20220906-PRIM-TSKG -5367 | Combarbalá slopes energy failures | 001076-20220926-TSKG-PRIM-4377 | LET-TSK-PRI-COM-2022-001
General | QS00 | 2022 | 09 | 7 | 001076-20220907-PRIM-TSKG-0062 (QS00) | 001076-20220907-PRIM-TSKG -5369 |  | 001076-20220923-TSKG-PRIM-4375 | LET-TSK-PRI-QS00-2022-020
General | QS00 | 2022 | 09 | 15 | 001076-20220915-PRIM-TSKG-0063 (QS00) | 001076-20220915-PRIM-TSKG -5374 | Contractor´s invoices related to July 2022
Llanos Blancos | QS02 | 2022 | 10 | 12 | 001076-20221012-PRIM-TSKG-0030 (QS02) | 001076-20221012-PRIM-TSKG -5401 |  | 001076-20221104-TSKG-PRIM-4411 | LET-TSK-PRI-LLB-2022-001
General | QS00 | 2022 | 10 | 13 | 001076-20221013-PRIM-TSKG-0064 (QS00) | 001076-20221013-PRIM-TSKG -5405 | Contractor´s invoices related to August 2022
Combarbalá | QS03 | 2022 | 10 | 24 | 001076-20221024-PRIM-TSKG-0018 (QS03) | 001076-20221024-PRIM-TSKG -5443 | Slope Affection | 001076-20221122-TSKG-PRIM-4431 | LET-TSK-PRI-COM-2022-002
General | QS00 | 2022 | 11 | 3 | 001076-20221102-PRIM-TSKG-0065 (QS00) | 001076-20221103-PRIM-TSKG -5464 |  | 001076-20221121-TSKG-PRIM-4429 | LET-TSK-PRI-QS00-2022-021
General | QS00 | 2022 | 11 | 12 | 001076-20221112-PRIM-TSKG-0066 (QS00) | 001076-20221112-PRIM-TSKG -5478 |  | 001076-20221115-TSKG-PRIM-4424 | LET-TSK-PRI-QS00-2022-022
General | QS00 | 2022 | 11 | 17 | 001076-20221117-PRIM-TSKG-0067 (QS00) | 001076-20221117-PRIM-TSKG -5486
General | QS00 | 2022 | 11 | 30 | 001076-20221130-PRIM-TSKG-0068 (QS00) | 001076-20221130-PRIM-TSKG-5502 | Response to 001076-20221121-TSKG-PRIM-4429
Llanos Blancos | QS02 | 2022 | 12 | 7 | 001076-20221207-PRIM-TSKG-0031 (QS02) | 001076-20221207-PRIM-TSKG -5507
Pajonales | QS01 | 2022 | 12 | 14 | 001076-20221214-PRIM-TSKG-0033 (QS01) | 001076-20221214-PRIM-TSKG -5515 | Flap Valve | 001076-20221216-TSKG-PRIM-4453 | LET-TSK-PRI-PAJ-2022-001
Llanos Blancos | QS02 | 2022 | 12 | 14 | 001076-20221214-PRIM-TSKG-0032 (QS02) | 001076-20221214-PRIM-TSKG -5516 | Flap Valve | 001076-20221216-TSKG-PRIM-4454 | LET-TSK-PRI-LLB-2022-002
Combarbalá | QS03 | 2022 | 12 | 14 | 001076-20221214-PRIM-TSKG-0019 (QS03) | 001076-20221214-PRIM-TSKG -5517 | Flap Valve | 001076-20221216-TSKG-PRIM-4455 | LET-TSK-PRI-COM-2022-003
Los Condores | QS04 | 2022 | 12 | 14 | 001076-20221214-PRIM-TSKG-0017 (QS04) | 001076-20221214-PRIM-TSKG -5518 | Flap Valve | 001076-20221216-TSKG-PRIM-4456 | LET-TSK-PRI-LCO-2022-001
Pajonales | QS01 | 2022 | 12 | 15 | 001076-20221215-PRIM-TSKG-0034 (QS01) | 001076-20221215-PRIM-TSKG -5520 | Pajonales Warranty Obligations
Pajonales | QS01 | 2022 | 12 | 21 | 001076-20221221-PRIM-TSKG-0035 (QS01) | 001076-20221221-PRIM-TSKG -5532 | Response TSK letter Warranty Claims period LET-TSK-PRI-PAJ-2022
Pajonales | QS01 | 2022 | 12 | 23 | 001076-20221223-PRIM-TSKG-0036 (QS01) | 001076-20221223-PRIM-TSKG -5533 | Noise Measurement Pajonales
Los Condores | QS04 | 2023 | 01 | 5 | 001076-20230105-PRIM-TSKG-0018 (QS04) | 001076-20230105-PRIM-TSKG -5540 | Los Condores slopes integrity failures
General | QS00 | 2023 | 01 | 13 | 001076-20230113-PRIM-TSKG-0069 (QS00) | 001076-20230113-PRIM-TSKG -5552 | Response to Contractor letter LET-TSK-PRI-QS00-2022/020

## TSKG-PRIM
Project Code | Assigned to | Year | Month | Day | Carpeta Mails | Mailing code TSK | Description | Response to letter/e-mail | Prime Letter Code | Prime Response Mailing Code | Observations
COM |  | 2019 | 12 | 03 | LET-TSK-PRI-COM-2019-002 | 001076-20191203-TSKG-PRIM-1840 | Force Majeure Combarbalá (QS03) |  | 001076-20200221-PRIM-TSKG-0007(QS03) | 001076-20200222-PRIM-TSKG -2187
COM |  | 2019 | 12 | 11 | LET-TSK-PRI-COM-2019-003 | 001076-20191211-TSKG-PRIM-1884 | Rejection of the Updated Schedule from October´s Monthly Report Combarbalá |  | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1974
COM |  | 2019 | 12 | 18 | LET-TSK-PRI-COM-2019-004 | 001076-20191218-TSKG-PRIM-1908 | Force Majeure Nov 27 (2d version) signed |  | 001076-20200221-PRIM-TSKG-0007(QS03) | 001076-20200222-PRIM-TSKG -2187
COM |  | 2020 | 02 | 12 | LET-TSK-PRI-COM-2020-001 | 001076-20200212-TSKG-PRIM-2085 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00) |  | 001076-20200316-PRIM-TSKG-0014(QS00) | 001076-20200317-PRIM-TSKG -2285
COM |  | 2020 | 03 | 02 | LET-TSK-PRI-COM-2020-002 | 001076-20200302-TSKG-PRIM-2133 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00) |  |  | 001076-20200317-PRIM-TSKG -2285 | email corrected the previous letter sent by TSK
COM |  | 2020 | 03 | 13 | LET-TSK-PRI-COM-2020-003 | 001076-20200313-TSKG-PRIM-2174 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00) |  |  | 001076-20200314-PRIM-TSKG -2272
COM |  | 2020 | 03 | 20 | LET-TSK-PRI-COM-2020-004 | 001076-20200320-TSKG-PRIM-2186 | Request for Guidelines and Actions on the Work due to Covid-19 |  | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320
LCO |  | 2019 | 12 | 03 | LET-TSK-PRI-LCO-2019-002 | 001076-20191203-TSKG-PRIM-1841 | Force Majeure Los Condores |  | 001076-20200221-PRIM-TSKG-0009(QS04) | 001076-20200222-PRIM-TSKG -2189
LCO |  | 2019 | 12 | 03 | LET-TSK-PRI-LCO-2019-003 | 001076-20191203-TSKG-PRIM-1843 | BBOSCH not doing erection works due to lach of Edif. Permit
LCO |  | 2019 | 12 | 03 | LET-TSK-PRI-LCO-2019-004 | 001076-20191203-TSKG-PRIM-1844 | Absence of Los Condores Edification Permit
LCO |  | 2019 | 12 | 18 | LET-TSK-PRI-LCO-2019-005 | 001076-20191218-TSKG-PRIM-1909 | e Force Majeure Nov 27 (2d version) signed |  | 001076-20200221-PRIM-TSKG-0009(QS04) | 001076-20200222-PRIM-TSKG -2189
LCO |  | 2020 | 03 | 13 | LET-TSK-PRI-LCO-2020-001 | 001076-20200313-TSKG-PRIM-2174 | Notification of Force Majeure for Covid-19 outbreak and quarantine imposed by Prime |  |  | 001076-20200314-PRIM-TSKG -2272
LCO |  | 2020 | 03 | 20 | LET-TSK-PRI-LCO-2020-002 | 001076-20200320-TSKG-PRIM-2186 | Request for Guidelines and Actions on the Work due to Covid-19 |  | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320
LCO |  | 2020 | 03 | 20 | LET-TSK-PRI-LCO-2020-003 | 001076-20200320-TSKG-PRIM-2190 | Force Majeure- Response to Prime´s letter | 001076-20200318-PRIM-TSKG-0002 (QS04) (March 16, 2020)
LLB |  | 2019 | 12 | 03 | LET-TSK-PRI-LLB-2019-002 | 001076-20191203-TSKG-PRIM-1839 | Force Majeure Llanos Blancos (QS02) |  | 001076-20200221-PRIM-TSKG-0010(QS02) | 001076-20200222-PRIM-TSKG -2190
LLB |  | 2019 | 12 | 11 | LET-TSK-PRI-LLB-2019-003 | 001076-20191211-TSKG-PRIM-1885 | ejection of the Updated Schedule from October´s Monthly Report Llanos Blancos |  | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1975
LLB |  | 2019 | 12 | 18 | LET-TSK-PRI-LLB-2019-004 | 001076-20191218-TSKG-PRIM-1907 | Force Majeure Nov 27 (2d version) signed |  | 001076-20200221-PRIM-TSKG-0010(QS02) | 001076-20200222-PRIM-TSKG -2190
LLB |  | 2020 | 02 | 12 | LET-TSK-PRI-LLB-2020-001 | 001076-20200212-TSKG-PRIM-2085 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00) |  | 001076-20200316-PRIM-TSKG-0002(QS02) | 001076-20200317-PRIM-TSKG -2282
LLB |  | 2020 | 02 | 14 | LET-TSK-PRI-LLB-2020-002 | 001076-20200214-TSKG-PRIM-2098 | Access Restrictions to site. |  | 001076-20200316-PRIM-TSKG-0003(QS02) | 001076-20200317-PRIM-TSKG -2284
LLB |  | 2020 | 03 | 02 | LET-TSK-PRI-LLB-2020-003 | 001076-20200302-TSKG-PRIM-2135 | ccess and available space hindrances - Llanos Blancos (QS02) |  | 001076-20200316-PRIM-TSKG-0003(QS02) | 001076-20200317-PRIM-TSKG -2284
LLB | JFA-JRL | 2020 | 03 | 02 | LET-TSK-PRI-LLB-2020-004 | 001076-20200302-TSKG-PRIM-2133 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00)
LLB |  | 2020 | 03 | 13 | LET-TSK-PRI-LLB-2020-005 | 001076-20200313-TSKG-PRIM-2174 | Force Majeure for Covid-19 outbreak and quarantine | LET-TSK-PRI-LLB-2020-001 LET-TSK-PRI-LLB-2020-004
LLB |  | 2020 | 03 | 20 | LET-TSK-PRI-LLB-2020-006 | 001076-20200320-TSKG-PRIM-2186 | Request for Guidelines and Actions on the Work due to Covid-19 |  | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320
LLB |  | 2020 | 03 | 20 | LET-TSK-PRI-LLB-2020-007 | 001076-20200320-TSKG-PRIM-2188 | Force Majeure for Covid-19 outbreak and quarantine | 001076-20200318-PRIM-TSKG-0004 (QS02) (March 16, 2020) | 001076-20200318-PRIM-TSKG-0004 (QS02)
PAJ |  | 2019 | 12 | 03 | LET-TSK-PRI-PAJ-2019-002 | 001076-20191203-TSKG-PRIM-1838 | Force Majeure Pajonales |  | 001076-20200221-PRIM-TSKG-0008(QS01) | 001076-20200222-PRIM-TSKG -2188
PAJ |  | 2019 | 12 | 18 | LET-TSK-PRI-PAJ-2019-004 | 001076-20191218-TSKG-PRIM-1906 | Letter re Force Majeure Nov 27 (2d version) signed |  | 001076-20200221-PRIM-TSKG-0008(QS01) | 001076-20200222-PRIM-TSKG -2188
PAJ |  | 2020 | 03 | 13 | LET-TSK-PRI-PAJ-2020-001 | 001076-20200313-TSKG-PRIM-2172 | loads information to be used for the main framework design | 001076-20200302-PRIM-TSKG-002 (QS01) | 001076-20200302-PRIM-TSKG-002 (QS01)
PAJ |  | 2020 | 03 | 13 | LET-TSK-PRI-PAJ-2020-002 | 001076-20200313-TSKG-PRIM-2174 | Notification of Force Majeure for Covid-19 outbreak and quarantine | 001076-20200311-PRIM-TSKG -2253: Covid-19 Preventive Measures |  | 001076-20200314-PRIM-TSKG -2272
PAJ |  | 2020 | 03 | 20 | LET-TSK-PRI-PAJ-2020-003 | 001076-20200320-TSKG-PRIM-2186 | Request for Guidelines and Actions on the Work due to Covid-19 |  | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320
PAJ |  | 2020 | 03 | 20 | LET-TSK-PRI-PAJ-2020-004 | 001076-20200320-TSKG-PRIM-2189 | FM Notification - Covid-19 | 001076-20200318-PRIM-TSKG-0003 (QS01)
QS00 |  | 2020 | 01 | 23 | LET-TSK-PRI-QS00-2020-001 | 001076-20200123-TSKG-PRIM-1996 | Rejection of the Updated Schedule from October´s Monthly Report Llanos Blancos |  | 001076-20200221-PRIM-TSKG-0006(QS00) | 001076-20200222-PRIM-TSKG -2186
SJV |  | 2019 | 12 | 03 | LET-TSK-PRI-SJV-2019-002 | 001076-20191203-TSKG-PRIM-1842 | Force Majeure San Javier (QS05) |  | 001076-20200221-PRIM-TSKG-0011(QS05) | 001076-20200222-PRIM-TSKG -2191
SJV |  | 2019 | 12 | 11 | LET-TSK-PRI-SJV-2019-003 | 001076-20191211-TSKG-PRIM-1886 | Rejection of the Updated Schedule from October´s Monthly Report San Javier |  | 001076-20191230-PRIM-TSKG-0004(QS00) | 001076-20200102-PRIM-TSKG -1973
SJV |  | 2019 | 12 | 18 | LET-TSK-PRI-SJV-2019-004 | 001076-20191218-TSKG-PRIM-1910 | Letter re Force Majeure Nov 27 (2d version) signed |  | 001076-20200221-PRIM-TSKG-0011(QS05) | 001076-20200222-PRIM-TSKG -2191
SJV |  | 2020 | 02 | 12 | LET-TSK-PRI-SJV-2020-001 | 001076-20200212-TSKG-PRIM-2085 | Delayed delivery plan of Main Utility Transformers. Force Majeure Event (QS00) |  | 001076-20200318-PRIM-TSKG-0003(QS05) | 001076-20200318-PRIM-TSKG -2295
SJV |  | 2020 | 03 | 02 | LET-TSK-PRI-SJV-2020-002 | 001076-20200302-TSKG-PRIM-2134 | Access restrictions to site - San Javier (QS05) |  | 001076-20200316-PRIM-TSKG-0002(QS05) | 001076-20200317-PRIM-TSKG -2283
SJV | JFA-JRL | 2020 | 03 | 02 | LET-TSK-PRI-SJV-2020-003 | 001076-20200302-TSKG-PRIM-2133 | Extended Dispatch Suspension of Utility Transformer. | new
SJV |  | 2020 | 03 | 13 | LET-TSK-PRI-SJV-2020-004 | 001076-20200313-TSKG-PRIM-2174 | Notification of Force Majeure for Covid-19 outbreak and quarantine | new |  | 001076-20200314-PRIM-TSKG -2272
SJV |  | 2020 | 03 | 20 | LET-TSK-PRI-SJV-2020-005 | 001076-20200320-TSKG-PRIM-2186 | Request for Guidelines and Actions on the Work due to Covid-19 |  | 001076-20200325-PRIM-TSKG-0007(QS00) | 001076-20200325-PRIM-TSKG -2320
SJV |  | 2020 | 03 | 20 | LET-TSK-PRI-SJV-2020-006 | 001076-20200320-TSKG-PRIM-2187 | Notification of Force Majeure for Covid-19 outbreak and quarantine |  | 001076-20200318-PRIM-TSKG-0004 (QS05)
LCO |  | 2020 | 03 | 27 | LET-TSK-PRI-LCO-2020-004 | 001076-20200327-TSKG-PRIM-2211 | General- Subcontractors issues |  | 001076-20200330-PRIM-TSKG-0003(QS04) | 001076-20200330-PRIM-TSKG -2336
LLB |  | 2020 | 03 | 27 | LET-TSK-PRI-LLB-2020-08 | 001076-20200327-TSKG-PRIM-2210 | General- Subcontractors issues |  | 001076-20200330-PRIM-TSKG-0005(QS02) | 001076-20200330-PRIM-TSKG -2334
PAJ |  | 2020 | 03 | 27 | LET-TSK-PRI-PAJ-2020-005 | 001076-20200327-TSKG-PRIM-2209 | General- Subcontractors issues |  | 001076-20200330-PRIM-TSKG-0004(QS01) | 001076-20200330-PRIM-TSKG -2333
COM |  | 2020 | 03 | 27 | LET-TSK-PRI-COM-2020-006 | 001076-20200327-TSKG-PRIM-2213 | General- Subcontractors issues |  | 001076-20200330-PRIM-TSKG-0003(QS03) | 001076-20200330-PRIM-TSKG -2335
SJV |  | 2020 | 03 | 27 | LET-TSK-PRI-SJV-2020-07 | 001076-20200327-TSKG-PRIM-2212 | General- Subcontractors issues |  | 001076-20200330-PRIM-TSKG-0005(QS05) | 001076-20200330-PRIM-TSKG -2337
COM |  | 2020 | 03 | 27 | LET-TSK-PRI-COM-2020-007 | 001076-20200327-TSKG-PRIM-2218 | ACM Mobilization (Events between Oct16-Nov30, 2019) | 001076-20200221-PRIM-TSKG – 0007 (QS03)
COM |  | 2020 | 03 | 28 | LET-TSK-PRI-COM-2020-008 | 001076-20200328-TSKG-PRIM-2221 | Rejected invoiced milestones. Feb20 Certification | 001076-20200320-PRIM-TSKG -2306 001076-20200305-TSKG-PRIM-2147
COM |  | 2020 | 03 | 28 | LET-TSK-PRI-COM-2020-009 | 001076-20200328-TSKG-PRIM-2226 | MTU Delayed Dispatch | 001076-20200316-PRIM-TSKG-0014 (QS00)
LCO |  | 2020 | 03 | 27 | LET-TSK-PRI-LCO-2020-005 | 001076-20200327-TSKG-PRIM-2217 | Events ocurred between Oct16-Nov2, and Nov2-30, 2019 | 001076-20200221-PRIM-TSKG – 0009 (QS04) (Feb 18th, 2020.
LCO |  | 2020 | 03 | 28 | LET-TSK-PRI-LCO-2020-006 | 001076-20200328-TSKG-PRIM-2222 | Rejected invoiced milestones. Feb20 Certification | 001076-20200320-PRIM-TSKG -2307 001076-20200305-TSKG-PRIM-2148
LLB |  | 2020 | 03 | 27 | LET-TSK-PRI-LLB-2020-009 | 001076-20200327-TSKG-PRIM-2219 | Events ocurred between Oct16-Nov2, and Nov2-30, 2019 | 001076-20200221-PRIM-TSKG – 0010 (QS02)
LLB |  | 2020 | 03 | 28 | LET-TSK-PRI-LLB-2020-010 | 001076-20200328-TSKG-PRIM-2220 | Rejected invoiced milestones. Feb20 Certification | 001076-20200320-PRIM-TSKG -2310 001076-20200305-TSKG-PRIM-2146
LLB |  | 2020 | 03 | 28 | LET-TSK-PRI-LLB-2020-011 | 001076-20200328-TSKG-PRIM-2224 | Delayed Dispatch of Utility Transformer | 001076-20200316-PRIM-TSKG-0002(QS02)
LLB |  | 2020 | 03 | 28 | LET-TSK-PRI-LLB-2020-012 | 001076-20200328-TSKG-PRIM-2229 | Restricted Access to the Facility Site | 001076-20200316-PRIM-TSKG-0003 (QS02), (Mar9, 20)
LLB |  | 2020 | 04 | 17 | LET-TSK-PRI-LLB-2020-013 | 001076-20200417-TSKG-PRIM-2306 | UNLOADING PLANNED DATES - KNAUF INTERNAL ACCESS BLOCKED BY LIQUID GAS TANK TRUCK |  | 001076-20200602-PRIM-TSKG-0008(QS02) | 001076-20200603-PRIM-TSKG -2630
PAJ |  | 2020 | 03 | 27 | LET-TSK-PRI-PAJ-2020-006 | 001076-20200327-TSKG-PRIM-2216 | Events ocurred between Oct16-Nov2, and Nov2-30, 2019 | 001076-20200221-PRIM-TSKG-0008 (QS01) ( Feb18, 20)
PAJ |  | 2020 | 03 | 28 | LET-TSK-PRI-PAJ-2020-007 | 001076-20200328-TSKG-PRIM-2219 | Rejected invoiced milestones. Feb20 Certification | 001076-20200320-PRIM-TSKG -2304 001076- 20200305-TSKG-PRIM-2145
SJV |  | 2020 | 03 | 27 | LET-TSK-PRI-SJV-2020-008 | 001076-20200327-TSKG-PRIM-2220 | Events ocurred between Oct16-Nov2, and Nov2-30, 2019 | 001076-20200221-PRIM-TSKG – 0011 (QS05)
SJV |  | 2020 | 03 | 28 | LET-TSK-PRI-SJV-2020-009 | 001076-20200328-TSKG-PRIM-2223 | Rejected invoiced milestones. Feb20 Certification | 001076-20200320-PRIM-TSKG -2308 001076-20200305-TSKG-PRIM-2149
SJV |  | 2020 | 03 | 28 | LET-TSK-PRI-SJV-2020-010 | 001076-20200328-TSKG-PRIM-2225 | Delayed Dispatch of Utility Transformer | 001076-20200318-PRIM-TSKG-0003(QS05)
SJV |  | 2020 | 03 | 28 | LET-TSK-PRI-SJV-2020-011 | 001076-20200328-TSKG-PRIM-2230 | Restricted Access to the Facility Site | 001076-20200316-PRIM-TSKG-0002(QS05), (Mar16,20)
QS00 |  | 2020 | 04 | 01 | LET-TSK-PRI-QS00-2020-003 | 001076-20200401-TSKG-PRIM-2248 | Requested Change in Work MEDIUM VOLTAGE CABLES HI-POT TEST (QS00): |  | 001076-20200422-PRIM-TSKG-0009(QS00) | 001076-20200422-PRIM-TSKG -2440
COM |  | 2020 | 04 | 24 | LET-TSK-PRI-COM-2020-010 | 001076-20200424-TSKG-PRIM-2323 | Covid-19 Subcontractors Notices and Preventive (Follow-up) |  | 001076-20200526-PRIM-TSKG-0004(QS03) | 001076-20200527-PRIM-TSKG -2593
LCO |  | 2020 | 04 | 24 | LET-TSK-PRI-LCO-2020-007 | 001076-20200424-TSKG-PRIM-2324 | Covid-19 Subcontractors Notices and Preventive (Follow-up) |  | 001076-20200526-PRIM-TSKG-0004(QS04) | 001076-20200527-PRIM-TSKG -2594
LLB |  | 2020 | 04 | 24 | LET-TSK-PRI-LLB-2020-014 | 001076-20200424-TSKG-PRIM-2322 | Covid-19 Subcontractors Notices and Preventive (Follow-up) |  | 001076-20200526-PRIM-TSKG-0007(QS02) | 001076-20200527-PRIM-TSKG -2596
PAJ |  | 2020 | 04 | 24 | LET-TSK-PRI-PAJ-2020-008 | 001076-20200424-TSKG-PRIM-2321 | Covid-19 Subcontractors Notices and Preventive (Follow-up) |  | 001076-20200526-PRIM-TSKG-0008(QS01) | 001076-20200527-PRIM-TSKG -2598
SJV |  | 2020 | 04 | 24 | LET-TSK-PRI-SJV-2020-012 | 001076-20200424-TSKG-PRIM-2325 | Covid-19 Subcontractors Notices and Preventive (Follow-up) |  | 001076-20200526-PRIM-TSKG-0006(QS05) | 001076-20200527-PRIM-TSKG -2595
PAJ |  | 2020 | 04 | 27 | LET-TSK-PRI-PAJ-2020-009 | 001076-20200427-TSKG-PRIM-2335 | Readiness for Signal Testing (QS01) |  | 001076-20200430-PRIM-TSKG-0005(QS01) | 001076-20200430-PRIM-TSKG -2475
PAJ |  | 2020 | 05 | 04 | LET-TSK-PRI-PAJ-2020-010 | 001076-20200504-TSKG-PRIM-2347 | Pajonales HV main frame internonnection |  | 001076-20200608-PRIM-TSKG-0013(QS01) | 001076-20200609-PRIM-TSKG -2654
QS00 |  | 2020 | 04 | 24 | LET-TSK-PRI-QS00-2020-004 | 001076-20200424-TSKG-PRIM-2326 | Change in Work MEDIUM VOLTAGE CABLES HI-POT TEST (QS00) |  | 001076-20200526-PRIM-TSKG-0007(QS01) | 001076-20200527-PRIM-TSKG -2597
QS00 |  | 2020 | 05 | 04 | LET-TSK-PRI-QS00-2020-005 | 001076-20200504-TSKG-PRIM-2348 | Spare Parts |  | 001076-20200914-PRIM-TSKG-0011(QS00) | 001076-20200914-PRIM-TSKG -3106
COM | BW | 2020 | 05 | 04 | LET-TSK-PRI-COM-2020-011 | 001076-20200504-TSKG-PRIM-2351 | Potable Water System
LCO | BW | 2020 | 05 | 04 | LET-TSK-PRI-LCO-2020-008 | 001076-20200504-TSKG-PRIM-2352 | Potable Water System
LLB | BW | 2020 | 05 | 04 | LET-TSK-PRI-LLB-2020-015 | 001076-20200504-TSKG-PRIM-2350 | Potable Water System
PAJ |  | 2020 | 05 | 04 | LET-TSK-PRI-PAJ-2020-011 | 001076-20200504-TSKG-PRIM-2349 | Voided | anulado por TSK a través de mail 001076-20200512-TSKG-PRIM-2403 | Voided | 001076-20200512-TSKG-PRIM-2403
SJV | BW | 2020 | 05 | 04 | LET-TSK-PRI-SJV-2020-013 | 001076-20200504-TSKG-PRIM-2353 | Potable Water System
PAJ |  | 2020 | 05 | 05 | LET-TSK-PRI-PAJ-2020-013 | 001076-20200505-TSKG-PRIM-2363 | Readiness for Signal Testing |  | 001076-20200605-PRIM-TSKG-0012(QS01) | 001076-20200609-PRIM-TSKG -2653
PAJ |  | 2020 | 05 | 05 | LET-TSK-PRI-PAJ-2020-014 | 001076-20200505-TSKG-PRIM-2357 | Readiness for Signal Testing |  | 001076-20200526-PRIM-TSKG-0009(QS01) | 001076-20200527-PRIM-TSKG -2599
PAJ |  | 2020 | 05 | 12 | LET-TSK-PRI-PAJ-2020-015 | 001076-20200512-TSKG-PRIM-2403 | Potable Water System, |  | 001076-20200526-PRIM-TSKG-0004(QS03) | 001076-20200527-PRIM-TSKG -2593
PAJ |  | 2020 | 05 | 12 | LET-TSK-PRI-PAJ-2020-016 | 001076-20200512-TSKG-PRIM-2407 | Pajonales Permit PAS 157 Letter of Concern |  | 001076-20200615-PRIM-TSKG-0014(QS01) | 001076-20200616-PRIM-TSKG -2688
COM | BW | 2020 | 05 | 18 | LET-TSK-PRI-COM-2020-012 | 001076-20200518-TSKG-PRIM-2424 | Sewage water system and permit
COM | JFA-JRL | 2020 | 05 | 18 | LET-TSK-PRI-COM-2020-013 | 001076-20200518-TSKG-PRIM-2416 | update on COVID
LCO | BW | 2020 | 05 | 18 | LET-TSK-PRI-LCO-2020-009 | 001076-20200518-TSKG-PRIM-2425 | Sewage water
LCO |  | 2020 | 05 | 18 | LET-TSK-PRI-LCO-2020-010 | 001076-20200518-TSKG-PRIM-2419 | Follow up on Los Cóndores Force Majeure Covid-19 |  | 001076-20200526-PRIM-TSKG-0004(QS04) | 001076-20200527-PRIM-TSKG -2594
LLB | BW | 2020 | 05 | 18 | LET-TSK-PRI-LLB-2020-016 | 001076-20200518-TSKG-PRIM-2423 | Sewage water | new
LLB |  | 2020 | 05 | 18 | LET-TSK-PRI-LLB-2020-017 | 001076-20200518-TSKG-PRIM-2418 | Follow up on Llanos Blancos Force Majeure Covid-19 |  | 001076-20200526-PRIM-TSKG-0007(QS02) | 001076-20200527-PRIM-TSKG -2596
PAJ | BW | 2020 | 05 | 18 | LET-TSK-PRI-PAJ-2020-012 | 001076-20200518-TSKG-PRIM-2422 | Sewage water | new
PAJ |  | 2020 | 05 | 18 | LET-TSK-PRI-PAJ-2020-017 | 001076-20200518-TSKG-PRIM-2415 | Follow up on Pajonales Force Majeure Covid-19 |  | 001076-20200526-PRIM-TSKG-0008(QS01) | 001076-20200527-PRIM-TSKG -2598
SJV | BW | 2020 | 05 | 18 | LET-TSK-PRI-SJV-2020-014 | 001076-20200518-TSKG-PRIM-2426 | Sewage water | new
SJV |  | 2020 | 05 | 18 | LET-TSK-PRI-SJV-2020-015 | 001076-20200518-TSKG-PRIM-2417 | Follow up on San Javier Force Majeure Covid-19 |  | 001076-20200526-PRIM-TSKG-0006(QS05) | 001076-20200527-PRIM-TSKG -2595
PAJ | MH | 2020 | 05 | 22 | LET-TSK-PRI-PAJ-2020-018 | 001076-20200522-TSKG-PRIM-2448 | readiness for signal testing
PAJ |  | 2020 | 05 | 22 | LET-TSK-PRI-PAJ-2020-019 | 001076-20200522-TSKG-PRIM-2449 | Pajonales 87L Test |  | 001076-20200602-PRIM-TSKG-0010(QS01) | 001076-20200603-PRIM-TSKG -2631
PAJ |  | 2020 | 06 | 01 | LET-TSK-PRI-PAJ-2020-020 | 001076-20200601-TSKG-PRIM-2476 | Signal testing |  | 001076-20200707-PRIM-TSKG-0017(QS01) | 001076-20200708-PRIM-TSKG -2795
LLB |  | 2020 | 06 | 02 | LET-TSK-PRI-LLB-2020-018 | 001076-20200602-TSKG-PRIM-2478 | Contrators issues - Hinderances |  | 001076-20200710-PRIM-TSKG-0011(QS02) | 001076-20200710-PRIM-TSKG -2816
QS00 |  | 2020 | 06 | 02 | LET-TSK-PRI-QS00-2020-006 | 001076-20200602-TSKG-PRIM-2480 | Electrical Tests -MV calbes and Tan Delta |  | 001076-20200707-PRIM-TSKG-0010(QS00) | 001076-20200708-PRIM-TSKG -2793
COM |  | 2020 | 06 | 02 | LET-TSK-PRI-COM-2020-014 | 001076-20200602-TSKG-PRIM-2479 | Contrators issues - Hinderances |  | 001076-20200713-PRIM-TSKG-0005(QS03) | 001076-20200717-PRIM-TSKG -2851
LCO |  | 2020 | 06 | 08 | LET-TSK-PRI-LCO-2020-011 | 001076-20200608-TSKG-PRIM-2503 | Contrators issues - Hinderances |  | 001076-20200630-PRIM-TSKG-0005(QS04) | 001076-20200630-PRIM-TSKG -2758
LLB |  | 2020 | 06 | 08 | LET-TSK-PRI-LLB-2020-019 | 001076-20200608-TSKG-PRIM-2505 | MAIN ELECTRICAL EQUIPMENT - UNLOADING PLANNED DATES - KNAUF INTERNAL ACCESS BLOCKED BY LIQUID GAS TANK TRUCK |  | 001076-20200706-PRIM-TSKG-0009(QS02) | 001076-20200706-PRIM-TSKG -2784
PAJ |  | 2020 | 06 | 09 | LET-TSK-PRI-PAJ-2020-021 | 001076-20200609-TSKG-PRIM-2508 | Hinerances due to covid |  | 001076-20200630-PRIM-TSKG-0015(QS01) | 001076-20200630-PRIM-TSKG -2760
SJV |  | 2020 | 06 | 08 | LET-TSK-PRI-SJV-2020-016 | 001076-20200608-TSKG-PRIM-2504 | Alleged Covid impact |  | 001076-20200630-PRIM-TSKG-0008(QS05) | 001076-20200630-PRIM-TSKG -2759
PAJ |  | 2020 | 06 | 15 | LET-TSK-PRI-PAJ-2020-022 | 001076-20200615-TSKG-PRIM-2522 | Gatehouse, 87L and Comtrade |  | 001076-20200707-PRIM-TSKG-0016(QS01) | 001076-20200708-PRIM-TSKG -2794
PAJ | MH | 2020 | 06 | 15 | LET-TSK-PRI-PAJ-2020-023 | 001076-20200615-TSKG-PRIM-2523 | readiness for signal testing
SJV |  | 2020 | 06 | 15 | LET-TSK-PRI-SJV-2020-017 | 001076-20200615-TSKG-PRIM-2524 | Acess to site |  | 001076-20200724-PRIM-TSKG-0009(QS05) | 001076-20200726-PRIM-TSKG -2877
LLB |  | 2020 | 06 | 19 | LET-TSK-PRI-LLB-2020-020 | 001076-20200619-TSKG-PRIM-2535 | FM Covid-19- Preventive Measures |  |  | 001076-20200622-PRIM-TSKG -2724
COM | JFA-JRL | 2020 | 07 | 01 | LET-TSK-PRI-COM-2020-015 | 001076-20200701-TSKC-PRIM-0275.03 | Positive Cases of COVID
PAJ |  | 2020 | 07 | 02 | LET-TSK-PRI-PAJ-2020-023 | 001076-20200702-TSKG-PRIM-2570 | TSK confirms that Change In Work related to modifications to design of PAS-157 was submitted to Prime LET-TSK-PRI-PAJ-2020/16 (QS01) | 001076-20200615-PRIM-TSKG-0014 (QS01)
PAJ |  | 2020 | 07 | 13 | LET-TSK-PRI-PAJ-2020-024 | 001076-20200713-TSKG-PRIM-2600 | COVID |  | 001076-20200727-PRIM-TSKG-0018(QS01) | 001076-20200729-PRIM-TSKG -2908
SJV |  | 2020 | 07 | 13 | LET-TSK-PRI-SJV-2020-018 | 001076-20200713-TSKG-PRIM-2601 | COVID |  | 001076-20200727-PRIM-TSKG-0010 (QS05) | 001076-20200729-PRIM-TSKG -2909
LLB |  | 2020 | 07 | 13 | LET-TSK-PRI-LLB-2020-022 | 001076-20200713-TSKG-PRIM-2602 | COVID |  | 001076-20200727-PRIM-TSKG-0012(QS02) | 001076-20200729-PRIM-TSKG -2907
LLB | JFA-JRL | 2020 | 07 | 13 | LET-TSK-PRI-LLB-2020-021 | 001076-20200713-TSKG-PRIM-2603 | RESUME OF WORK LLB (QS02)
PAJ |  | 2020 | 07 | 14 | LET-TSK-PRI-PAJ-2020-025 | 001076-20200714-TSKG-PRIM-2607 | AFECCION POSITIVOS COVID 30/6/20 Y CONTACTOS ESTRECHOS A PROGRAMA PAJONALES (QS01) |  | 001076-20200819-PRIM-TSKG-0020(QS01) | 001076-20200820-PRIM-TSKG -3004
LLB | JFA-JRL | 2020 | 07 | 14 | LET-TSK-PRI-LLB-2020-022 | 001076-20200714-TSKG-PRIM-2608 | COVID | new
PAJ |  | 2020 | 07 | 14 | LET-TSK-PRI-PAJ-2020-026 | 001076-20200714-TSKG-PRIM-2609 | “Technical report - HV Frame calculations in Pajonales” | 001076-20200608-PRIM-TSKG-0013(QS01)
PAJ |  | 2020 | 07 | 17 | LET-TSK-PRI-PAJ-2020-027 | 001076-20200717-TSKG-PRIM-2627 | AFECCION POSITIVOS COVID 30/6/20 Y CONTACTOS ESTRECHOS A PROGRAMA PAJONALES (QS01) |  | 001076-20200811-PRIM-TSKG-0019(QS01) | 001076-20200811-PRIM-TSKG -2965
COM |  | 2020 | 07 | 24 | LET-TSK-PRI-COM-2020-016 | 001076-20200724-TSKG-PRIM-2642 | Acess Road |  | 001076-20200811-PRIM-TSKG-0006(QS03) | 001076-20200811-PRIM-TSKG -2962
LCO |  | 2020 | 07 | 24 | LET-TSK-PRI-LCO-2020-012 | 001076-20200724-TSKG-PRIM-2643 | Extraordinary work authorization and PMF perormance |  | 001076-20200811-PRIM-TSKG-0006(QS04) | 001076-20200811-PRIM-TSKG -2963
LLB |  | 2020 | 07 | 24 | LET-TSK-PRI-LLB-2020-023 | 001076-20200724-TSKG-PRIM-2641 | Extraordinary work authorization and PMF perormance |  | 001076-20200811-PRIM-TSKG-0013(QS02) | 001076-20200811-PRIM-TSKG -2964
LLB |  | 2020 | 07 | 31 | LET-TSK-PRI-LLB-2020-024 | 001076-20200731-TSKG-PRIM-2671 | FM Covid-19 – 2nd Stoppage of Works | new | no letter | 001076-20200811-PRIM-TSKG -2961
SJV |  | 2020 | 08 | 21 | LET-TSK-PRI-SJV-2020-019 | 001076-20200821-TSKG-PRIM-2723 | Access to the site | 001076-20200724-PRIM-TSKG-0009 (QS05)
PAJ |  | 2020 | 08 | 21 | LET-TSK-PRI-PAJ-2020-031 | 001076-20200821-TSKG-PRIM-2724 | COVID | 001076-20200811-PRIM-TSKG-0019 (QS01)
PAJ |  | 2020 | 08 | 21 | LET-TSK-PRI-PAJ-2020-030 | 001076-20200821-TSKG-PRIM-2725 | various topics | 001076-20200727-PRIM-TSKG-0018 (QS01)
PAJ |  | 2020 | 08 | 21 | LET-TSK-PRI-PAJ-2020-029 | 001076-20200820-TSKG-PRIM-2720 | readiness for signal testing | 001076-20200707-PRIM-TSKG-0017(QS01)
PAJ |  | 2020 | 08 | 21 | LET-TSK-PRI-PAJ-2020-028 | 001076-20200820-TSKG-PRIM-2719 | readiness for signal testing | 001076-20200707-PRIM-TSKG-0016 (QS01)
LLB |  | 2020 | 08 | 21 | LET-TSK-PRI-LLB-2020-026 | 001076-20200821-TSKG-PRIM-2728 | various topics | 001076-20200811-PRIM-TSKG-0013 (QS02
LLB |  | 2020 | 08 | 21 | LET-TSK-PRI-LLB-2020-025 | 001076-20200821-TSKG-PRIM-2722 | access to the site | 001076-20200706-PRIM-TSKG-0009 (QS02)
LCO |  | 2020 | 08 | 21 | LET-TSK-PRI-LCO-2020-013 | 001076-20200821-TSKG-PRIM-2726 | various topics | 001076-20200811-PRIM-TSKG-0006 (QS04)
COM |  | 2020 | 08 | 21 | LET-TSK-PRI-COM-2020-017 | 001076-20200821-TSKG-PRIM-2727 | various topics | 001076-20200811-PRIM-TSKG-0006 (QS03)
QS00 | JFA-JRL | 2020 | 09 | 3 | LET-TSK-PRI-QS00-2020-009 | 001076-20200903-TSKG-PRIM-2778 | Labor Strike of Truck Drivers Labor Union-Force Majeure | new
PAJ |  | 2020 | 09 | 21 | LET-TSK-PRI-PAJ-2020-032 | 001076-20200921-TSKG-PRIM-2813 | COVID | 001076-20200819-PRIM-TSKG-0020 (QS01)
LLB | BW | 2020 | 09 | 21 | LET-TSK-PRI-LLB-2020-027 | 001076-20200921-TSKG-PRIM-2812 | Sewage system Facility Site
COM | BW | 2020 | 09 | 21 | LET-TSK-PRI-COM-2020-018 | 001076-20200921-TSKG-PRIM-2814 | Sewage system Facility Site
LCO | BW | 2020 | 09 | 21 | LET-TSK-PRI-LCO-2020-014 | 001076-20200921-TSKG-PRIM-2815 | Final reception of PAS 156
QS00 |  | 2020 | 09 | 23 | LET-TSK-PRI-QS00-2020-010 | 001076-20200923-TSKG-PRIM-2823 | Surge in Safety Incidents | PEQ-2020-049
LCO | BW | 2020 | 09 | 23 | LET-TSK-PRI-LCO-2020-015 | 001076-20200923-TSKG-PRIM-2822 | Sewage system Facility Site
PAJ | BW | 2020 | 09 | 23 | LET-TSK-PRI-PAJ-2020-012 | RE_001076-20200910-PRIM-TSKG-3088 | Sewage water system and permit
QS00 | JFA-JRL | 2020 | 09 | 30 | LET-TSK-PRI-QS00-2020-012 | 001076-20200930-TSKG-PRIM-2840 | Final approval of the construction activities | 001076-20201205-PRIM-TSKG-0016 (QS00) |  | 001076-20201207-PRIM-TSKG -3460
SJV | JFA-JRL | 2020 | 10 | 26 | LET-TSK-PRI-SJV-2020-020 | 001076-20201026-TSKG-PRIM-2883 | San Javier access restriction
QS00 | CS | 2020 | 10 | 26 | LET-TSK-PRI-QS00-2020-011 | 001076-20201026-TSKG-PRIM-2882 | Process for review and selection of recommended Primary Spare Parts
LLB | JFA-JRL | 2020 | 10 | 26 | LET-TSK-PRI-LLB-2020-028 | 001076-20201023-TSKC-PRIM-0161.02 | Llanos Blancos- Coquimbo Area - Phase 2 Transition
LCO | JFA-JRL | 2020 | 10 | 26 | LET-TSK-PRI-LCO-2020-016 | 001076-20201026-TSKG-PRIM-2881 | Additional area for temporary facilities
LLB | MH-JFA | 2020 | 11 | 2 | LET-TSK-PRI-PAJ-2020-033 | 001076-20201102-TSKG-PRIM-2897 | Answer to: 001076-20201022-PRIM-TSKG -3253: Pajonales- : Habilitación de acceso a red 172.20.100.0/24
PAJ |  | 2020 | 11 | 10 | LET-TSK-PRI-PAJ-2020-034 | 001076-20201110-TSKG-PRIM-2918 | Achievement of Initial Synchronization. Follow-up: 001076-20201016-TSKG-PRIM-2870: Pajonales Start-Up activities. Permit to Synchronize with Utility Grid (QS01) | 001076-20201118-PRIM-TSKG-0022(QS01) |  | 001076-20201118-PRIM-TSKG -3370
QS00 |  | 2020 | 12 | 4 | LET-TSK-PRI-QS00-2020-013 | 001076-20201204-TSKG-PRIM-2964 | Answer to Labor lawsuits filed against Owner and its affiliates (QS00) |  | 001076-20201214-PRIM-TSKG-0018(QS00) | 001076-20201216-PRIM-TSKG -3496
PAJ |  | 2020 | 12 | 15 | LET-TSK-PRI-PAJ-2020-035 | 001076-20201215-TSKG-PRIM-2986 | Contractor's Net Electrical Output Test (QS01) |  |  | 001076-20201216-PRIM-TSKG -3494
PAJ |  | 2020 | 12 | 22 | LET-TSK-PRI-PAJ-2020-0036 | 001076-20201221-TSKG-PRIM-2994 | informing that Contractor’s Efficiency Test for Pajonales Facility has been performed and achieved
PAJ |  | 2020 | 12 | 24 | LET-TSK-PRI-PAJ-2020-037 | 001076-20201224-TSKG-PRIM-3005 | Contractor's Noise Test Report: (QS01)
PAJ |  | 2020 | 12 | 31 | LET-TSK-PRI-PAJ-2020-038 | 001076-20201231-TSKG-PRIM-3022 | Notice of Achievement. Pajonales 100MW Substantial Completion (QS01):
QS00 |  | 2021 | 1 | 12 | LET-TSK-PRI-QS00-2021-001 | 001076-20210112-TSKG-PRIM-3044 | Response to 001076-20201214-PRIM-TSKG -3488: Letter 001076-20201210-PRIM-TSKG-0017(QS00) - Arch Flash Studies and Labeling:
LCO |  | 2021 | 1 | 20 | LET-TSK-PRI-CON-2021-0001 | 001076-20210120-TSKG-PRIM-3060 | Initial Syncronzation
LCO |  | 2021 | 1 | 29 | LET-TSK-PRI-LCO-2021-001 | 001076-20210129-TSKG-PRIM-3091 | Response to 001076-20210124-PRIM-TSKG -3614: reply to : 001076-20210111-TSKG-PRIM-3038: Los Condores Invoice certificate related to December 2020 (QS04):
LCO |  | 2021 | 1 | 29 | LET-TSK-PRI-LCO-2021-002 | 001076-20210129-TSKG-PRIM-3092 | Response to 001076-20210126-PRIM-TSKG -3625: Los Condores- CEN Pre-tests - P Máx/C Esp:: (QS04)
PAJ |  | 2020 | 2 | 1 | LET-TSK-PRI-PAJ-2021-001 | 001076-20210201-TSKG-PRIM-3096 | Notice of Achievement. Pajonales 100MW Substantial Completion (QS01) |  | 001076-20210221-PRIM-TSKG-0029 (QS01) | 001076-20210222-PRIM-TSKG -3751
PAJ |  | 2020 | 2 | 1 | LET-TSK-PRI-PAJ-2021-002 | 001076-20200201-TSKG-PRIM-3097 | Rejection of Payment Milestones
LCO |  | 2021 | 2 | 10 | LET-TSK-PRI-CON-2021-0003 | 001076-20210210-TSKG-PRIM-3139 | Contractor's Net Electrical Output Test
QS00 |  | 2021 | 2 | 11 | LET-TSK-PRI-QS00-2021-002 | 001076-20210211-TSKG-PRIM-03149 | Response to 001076-20210210-PRIM-TSKG -3680: Response to 001076-20210209-MTUA-PRIM-0111: Root-Cause Analysis: Step-Up Transformer Damage (QS01): |  |  | 001076-20210215-PRIM-TSKG -3708
COM |  | 2021 | 2 | 19 | LET-TSK-PRI-COM-2021-001 | 001076-20210219-TSKG-PRIM-3163 | Combarbala Sewage and Potable Water Systems (QS03)
LCO |  | 2021 | 2 | 19 | LET-TSK-PRI-LCO-2021-004 | 001076-20201119-TSKG-PRIM-3166 | informs Owner and Independent Engineer that Substantial Completion for Pajonales 100MW Project has been achieved. |  | 001076-20210224-PRIM-TSKG-0007 (QS04) | 001076-20210224-PRIM-TSKG -3782
PAJ |  | 2021 | 2 | 25 | LET-TSK-PRI-PAJ-2021-003 | 001076-20210225-TSKG-PRIM-3178 | Answer to: 001076-20210207-PRIM-TSKG -3657: Owner´s Letter - Retainage of Pajonlaes Project (QS01)
COM |  | 2021 | 3 | 8 | LET-TSK-PRI-COM-2021-001 | 001076-20210308-TSKG-PRIM-3224 | Response to 001076-20210305-PRIM-TSKG -3823: Response to 001076-20210222-TSKG-PRIM-3169: Combarbalá Sewage System (QS03): |  | 001076-20210328-PRIM-TSKG-0008 (QS03) | 001076-20210329-PRIM-TSKG -3916
QS00 |  | 2021 | 3 | 16 | LET-TSK-PRI-QS00-2021-004 | 001076-20210316-TSKG-PRIM-3247 | Response to Prime's suggested Change In Works Combarbalá Llanos Blancos and San Javier (QS00) |  | 001076-20210319-PRIM-TSKG-0020 (QS00) | 001076-20210319-PRIM-TSKG -3894
LLB |  | 2021 | 3 | 22 | LET-TSK-PRI-LLB-2021-001 | 001076-20210322-TSKG-PRIM-3263 | Change in Site Manager Llanos Blancos ( QS02):
SJV |  | 2021 | 3 | 22 | LET-TSK-PRI-SJV-2021-001 | 001076-20210322-TSKG-PRIM-3264 | Change in Site Manager San Javier ( QS05):
PAJ |  | 2021 | 5 | 1 | LET-TSK-PRI-PAJ-2021-004 | 001076-20210501-TSKG-PRIM-3362 | Contractor's Letter on Pajonales Substantial Completion Date (QS01)
LCO |  | 2021 | 5 | 1 | LET-TSK-PRI-LCO-2021-005 | 001076-20210501-TSKG-PRIM-3364 | Contractor's Letter on Los Condores Substantial Completion Date (QS04)
SJV |  | 2021 | 5 | 20 | LET-TSK-PRI-SJV-2021-002 | 001076-20210520-TSKG-PRIM-3399 | Response to 001076-20210519-PRIM-TSKG -4050: Notification of delay in backfeed at San Javier (QS05) |  | 001076-20210812-PRIM-TSKG-0013 (QS05) | 001076-20210812-PRIM-TSKG -4317
LLB |  | 2021 | 6 | 4 | LET-TSK-PRI-LLB-2021-002 | 001076-20210604-TSKG-PRIM-3432 | Response to 001076-20210528-PRIM-TSKG -4069: Letter 001076-20210528-PRIM-TSKG-0024(QS00) - Assistance Plan Letter Agreement
PAJ |  | 2021 | 6 | 14 | LET-TSK-PRI-PAJ-2021-005 | 001076-20210614-TSKG-PRIM-3456 | Response to 001076-20210528-PRIM-TSKG -4070: - Delay Liquidated Damages (QS01)
COM |  | 2021 | 6 | 18 | LET-TSK-PRI-COM-2021-002 | 001076-20210618-TSKG-PRIM-3466 | Interruption of Performance Tests suffered yesterday at the Combarbalá Facility
COM |  | 2021 | 6 | 27 | LET-TSK-PRI-COM-2021-003 | 001076-20210627-TSKG-PRIM-3492 | Notice to Owner. Achievement of Substantial Completion QSCOM75MW (QS03) |  | 001076-20210701-PRIM-TSKG-0010 (QS03) | 001076-20210701-PRIM-TSKG -4168
COM |  | 2021 | 7 | 7 | LET-TSK-PRI-COM-2021-004 | 001076-20210707-TSKG-PRIM-3513 | Response to: 001076-20210630-PRIM-TSKG -4164...: Combarbalá Reliability Test (QS03)
PAJ |  | 2021 | 7 | 9 | LET-TSK-PRI-PAJ-2021-006 | 001076-20210709-TSKG-PRIM-3517 | Delay Liquidated Damages (follow up).
SJV |  | 2021 | 7 | 29 | LET-TSK-PRI-SJV-2021-003 | 001076-20210729-TSKG-PRIM-3579 | Follow up 001076-20210520-TSKG-PRIM-3399: Response to 001076-20210519-PRIM-TSKG -4050: Notification of delay in backfeed at San Javier (QS05)
PAJ |  | 2021 | 8 | 18 | LET-TSK-PRI-PAJ-2021-007 | 001076-20210818-TSKG-PRIM-3625 | Answer to: 001076-20210727-PRIM-TSKG -4253: Pajonales - Status of Final Completion (QS01) |  | 001076-20210812-PRIM-TSKG-0013 (QS05) | 001076-20210812-PRIM-TSKG -4317
LCO |  | 2021 | 9 | 1 | LET-TSK-PRI-LCO-2021-006 | 001076-20210901-TSKG-PRIM-3656 | Answer to: 001076-20210825-PRIM-TSKG -4357: Letter 001076-20210825-PRIM-TSKG-0011 (QS04) |  | 001076-20210910-PRIM-TSKG-0012 (QS04) | 001076-20210910-PRIM-TSKG -4408
LLB |  | 2021 | 9 | 3 | LET-TSK-PRI-LLB-2021-002 | 001076-20210903-TSKG-PRIM-3680 | Response to 001076-20210831-PRIM-TSKG -4370: Llanos Blancos - Labor authority inspection (QS02)
QS00 |  | 2021 | 9 | 3 | LET-TSK-PRI-QS00-2021-005 | 001076-20210903-TSKG-PRIM-3668 | Quickstart Projects – Lien Waivers for Final Completion (QS00)
LLB |  | 2021 | 9 | 6 | LET-TSK-PRI-LLB-2021-003 | 001076-20210906-TSKG-PRIM-3681 | Answer to: 001076-20210828-PRIM-TSKG -4368: Letter 001076-20210828-PRIM-TSKG-0016 (QS02)- contractor´s updated to the Llanos Blancos schedule
COM |  | 2021 | 9 | 13 | LET-TSK-PRI-COM-2021-004 | 001076-20210910-TSKG-PRIM-3696 | Answer to 001076-20210911-PRIM-TSKG -4413: Combarbalá - Notice to Contractor of Assuming Care, Custody and Control (QS03)
SJV |  | 2021 | 10 | 1 | LET-TSK-PRI-SJV-2021-004 | 001076-20211001-TSKG-PRIM-3758 | Response to 001076-20210812-PRIM-TSKG-4317: San Javier-Owner´s Letter No. 001076-20210812-PRIM-TSKG-0013 (QS05)
QS00 |  | 2021 | 10 | 9 | LET-TSK-PRI-QS00-2021-006 | 001076-20211019-TSKG-PRIM-3804 | Quickstart Projects -Bejos Retainage (QS00)
LCO |  | 2021 | 11 | 6 | LET-TSK-PRI-LCO-2021-007 | 001076-20211106-TSKG-PRIM-3839 | Los Condores- Owner´s Letter No. 001076-20210910-PRIM-TSKG-0012 (QS04)
QS00 |  | 2022 | 1 | 13 | LET-TSK-PRI-QS00-2022-001 | 001076-20220113-TSKG-PRIM-4029 | Warranty Bonds
QS00 |  | 2022 | 1 | 17 | LET-TSK-PRI-QS00-2022-002 | 001076-20220117-TSKG-PRIM-4034 | Subcontractor Liabilities |  | 001076-20220119-PRIM-TSKG-0034 (QS00) | 001076-20220119-PRIM-TSKG -4817
QS00 |  | 2022 | 1 | 27 | LET-TSK-PRI-QS00-2022-003 | 001076-20220127-TSKG-PRIM-4052 | Follow up on correspondence 001076-20220119-PRIM-TSKG-0034 (QS00) - Subcontractor Liabilities (follow-up)
LCO |  | 2022 | 2 | 7 | LET-TSK-PRI-LCO-2021-001 | 001076-20220407-TSKG-PRIM-4074 | Damaged Equipment due to Prime wrongful operation |  | 001076-20220221-PRIM-TSKG-0015 (QS04) | 001076-20220221-PRIM-TSKG -4927
QS00 |  | 2022 | 2 | 10 | LET-TSK-PRI-QS00-2022-004 | 001076-20220210-TSKG-PRIM-4081 | Subcontractor Payments (second follow-up)
QS00 |  | 2022 | 3 | 18 | LET-TSK-PRI-QS00-2022-006 | 001076-20220318-TSKG-PRIM-4131 | Invoicing requirements related to January 2022
QS00 |  | 2022 | 3 | 28 | LET-TSK-PRI-QS00-2022-007 | 001076-20220328-TSKG-PRIM-4145 | Requirements and payment of Contractor's invoice |  | 001076-20220331-PRIM-TSKG -0040 (QS00) | 001076-20220331-PRIM-TSKG -5028
QS00 |  | 2022 | 4 | 11 | LET-TSK-PRI-QS00-2022-009 | 001076-20220411-TSKG-PRIM-4168 | Answer to Prime's letter 042. Contractor's invoices
SJV |  | 2022 | 4 | 11 | LET-TSK-PRI-SJV-2022-001 | 001076-20220411-TSKG-PRIM-4169 | Genset step-Up transformers - Alarm and Trip limits / Response to Prime's letter 0023 (QS05)
QS00 |  | 2022 | 4 | 13 | LET-TSK-PRI-QS00-2022-010 | 001076-20220413-TSKG-PRIM-4174 | Response Advance Payments Reimbursement Letter
QS00 |  | 2022 | 4 | 13 | LET-TSK-PRI-QS00-2022-011 | 001076-20220413-TSKG-PRIM-4175 | Response Delay LDs Letter
QS00 |  | 2022 | 4 | 18 | LET-TSK-PRI-QS00-2022-008 | 001076-20220418-TSKG-PRIM-4178 | Letter of Response SCADA SAT
QS00 |  | 2022 | 4 | 27 | LET-TSK-PRI-QS00-2022-012 | 001076-20220427-TSKG-PRIM-4190 | Letter of Response Raincaps / response to Owner´s letter No. 001076-20220413-PRIM-TSKG-0045 (QS00)
SJV |  | 2022 | 4 | 29 | LET-TSK-PRI-SJV-2022-002 | 001076-20220429-TSKG-PRIM-4197 | Response Letter SJV Water issues
LCO |  | 2022 | 5 | 9 | LET-TSK-PRI-LCO-2021-001 | 001076-20220509-TSKG-PRIM-4214 | Damaged Equipment due to Prime wrongful operation
QS00 |  | 2022 | 5 | 11 | LET-TSK-SGS-QS00-2022-001 | 001076-20220511-TSKG-PRIM-4224 | Siniestro Nº121493533 Motores con daños por agua
QS00 |  | 2022 | 5 | 20 | LET-TSK-PRI-QS00-2022-008 | 001076-20220520-TSKG-PRIM-4234 | Letter of Response SCADA SAT
QS00 |  | 2022 | 6 | 1 | LET-TSK-PRI-QS00-2022-014 | 001076-20220531-TSKG-PRIM-4256 | Letter of Response Case N° M-885-2020
QS00 |  | 2022 | 6 | 1 | LET-TSK-PRI-QS00-2022-015 | 001076-10220601-TSKG-PRIM-4257 | Maintenance of QS Plants (QS00)
QS00 |  | 2022 | 6 | 24 | LET-TSK-PRI-QS00-2022-016 | 001076-20220624-TSKG-PRIM-4298 | Offset and Payment of Award
QS00 |  | 2022 | 8 | 8 | LET-TSK-PRI-QS00-2022-017 | 001076-20220808-TSKG-PRIM-4344 | Response to Pending Critical Contractor's Permits
QS00 |  | 2022 | 9 | 14 | LET-TSK-PRI-QS00-2022-018 | 001076-20220914-TSKG-PRIM-4367 | Unauthorized Substantial Modifications
QS00 |  | 2022 | 9 | 23 | LET-TSK-PRI-QS00-2022-020 | 001076-20220923-TSKG-PRIM-4375 | Response to Pending Critical Contractor's Permits |  | 001076-20230113-PRIM-TSKG-0069 (QS00) | 001076-20230113-PRIM-TSKG -5552
COM |  | 2022 | 9 | 26 | LET-TSK-PRI-COM-2022-001 | 001076-20220926-TSKG-PRIM-4377 | Response Combarbalá Heavy Rain Event
LLB |  | 2022 | 11 | 4 | LET-TSK-PRI-LLB-2022-001 | 001076-20221104-TSKG-PRIM-4411 | Response to Noise Report Claim
QS00 |  | 2022 | 11 | 15 | LET-TSK-PRI-QS00-2022-022 | 001076-20221115-TSKG-PRIM-4424 | Letter of Response Case Nº O-6411-2020 [Crooker con Bejos SpA]
QS00 |  | 2022 | 11 | 21 | LET-TSK-PRI-QS00-2022-021 | 001076-20221121-TSKG-PRIM-4429 | Contractor's Firewalls, Passwords and Licenses |  | 001076-20221130-PRIM-TSKG-0068 (QS00) | 001076-20221130-PRIM-TSKG-5502
COM |  | 2022 | 11 | 22 | LET-TSK-PRI-COM-2022-002 | 001076-20221122-TSKG-PRIM-4431 | Response Combarbalá Slopes Integrity Failure
PAJ |  | 2022 | 12 | 16 | LET-TSK-PRI-PAJ-2022-001 | 001076-20221216-TSKG-PRIM-4453 | Response Ref. Flap Valve installation
LLB |  | 2022 | 12 | 16 | LET-TSK-PRI-LLB-2022-002 | 001076-20221216-TSKG-PRIM-4454 | Response Ref. Flap Valve installation
COM |  | 2022 | 12 | 16 | LET-TSK-PRI-COM-2022-003 | 001076-20221216-TSKG-PRIM-4455 | Response Ref. Flap Valve installation
LCO |  | 2022 | 12 | 16 | LET-TSK-PRI-LCO-2022-001 | 001076-20221216-TSKG-PRIM-4456 | Response Ref. Flap Valve installation
PAJ |  | 2022 | 12 | 19 | LET-TSK-PRI-PAJ-2022-002 | 001076-20221219-TSKG-PRIM-4458 | Pajonales Warranty Period |  | 001076-20221221-PRIM-TSKG-0035 (QS01) | 001076-20221221-PRIM-TSKG -5532